## Logs
Team | Member | Week | Tasks | Planned Hours | Realized Hours | Narrative | Accomplishments | Additional Responsibilities | Reason of Failure | Team | Member
Printsan | Elif Meriç | 1 | Product Owner | 3 | 3 | Elif find us a customer. Printsan is a textile company and needs a website. |  | Help Planning |  | Printsan | Elif Meriç
Printsan | Kadir Batuhan Demir | 1 | Product Manager | 3 | 3 | We do some researches for website ideas,themes. Make distribution of tasks. |  | Help Planning |  |  | Kadir Batuhan Demir
Printsan | Muratcan Tüfekçi | 1 | Front-End Developer | 3 | 3 |  |  | Help Planning |  |  | Muratcan Tüfekçi
Printsan | Muhammet Aksoy | 1 | Front-End Developer | 3 | 3 |  |  | Help Planning |  |  | Muhammet Aksoy
Printsan | Çağla Çöpürkaya | 1 | Tester | 3 | 3 |  |  | Help Planning |  |  | Çağla Çöpürkaya
Printsan | Ulaş Yılmaz | 1 | Back-end Developer | 3 | 3 |  |  | Help Planning |  |  | Ulaş Yılmaz
Printsan | Barış Baran Aslan | 1 | Back-end Developer | 3 | 3 |  |  | Help Planning |  |  | Barış Baran Aslan
Printsan | Abdullah Oranqaı | 1 | Analyst | 3 | 3 |  |  | Help Planning |  |  | Abdullah Oranqaı
Printsan | Elif Meriç | 2 | Product Owner | 3 | 3 | Make meetings with customer and explain to us. Open a Jira and help for Feasibility Report. | Feasibility Report | Feasibility Report
Printsan | Kadir Batuhan Demir | 2 | Product Manager | 3 | 3 | Planning for choosen theme and prepare Mock-ups for report and Front-End developers. | Mock-ups | Mock-ups
Printsan | Muratcan Tüfekçi | 2 | Front-End Developer | 3 | 3 | Helps for Back-End table decisions. |  | Helping Database
Printsan | Muhammet Aksoy | 2 | Front-End Developer | 3 | 3 | Helps for Back-End table decisions. |  | Helping Database
Printsan | Çağla Çöpürkaya | 2 | Tester | 3 | 3 | Because of Feasibility Report experience, she is the main responsible. | Feasibility Report | Feasibilty Report
Printsan | Ulaş Yılmaz | 2 | Back-end Developer | 3 | 3 | Decide create tasks of tables. | General scheme | Decide Database
Printsan | Barış Baran Aslan | 2 | Back-end Developer | 3 | 3 | Decide create tasks of tables.
Printsan | Abdullah Oranqaı | 2 | Analyst | 3 | 3 | Design tables and make diagrams for the report. | Feasibility Report | Feasibilty Report
Printsan | Elif Meriç | 3 | Product Owner | 3.5 | 2.5 | Design decisions |  | Scrum Master
Printsan | Kadir Batuhan Demir | 3 | Product Manager | 3.5 | 2.5 |  |  | Analyze Help
Printsan | Muratcan Tüfekçi | 3 | Front-End Developer | 3.5 | 2.5 | Created most of the mainpage.
Printsan | Muhammet Aksoy | 3 | Front-End Developer | 3.5 | 2.5 |  | Mainpage working
Printsan | Çağla Çöpürkaya | 3 | Tester | 3.5 | 2.5 | Prepare the projectcharter document. | ProjectCharter
Printsan | Ulaş Yılmaz | 3 | Back-end Developer | 3.5 | 2.5 | Make database tables and connections on the MsSql | Tables
Printsan | Barış Baran Aslan | 3 | Back-end Developer | 3.5 | 2.5
Printsan | Abdullah Oranqaı | 3 | Analyst | 3.5 | 2.5 | Prepare the projectcharter document. | ProjectCharter
Printsan | Elif Meriç | 4 | Product Owner | 2 | 5 | Makes a meeting with customer for final design decisions and get all requirement infos. | Meeting with customer. | Report helping
Printsan | Kadir Batuhan Demir | 4 | Product Manager | 2 | 2 | Report updates and join conference with customer. Do detailed mock ups with design decisions and writing them as a report for developers. | Design Writing Report | Design analyze helping
Printsan | Muratcan Tüfekçi | 4 | Front-End Developer | 2 | 5 | Main page design done with final form.Ready for dynamic data.Video clip and vision/mission designs will be revised.
Printsan | Muhammet Aksoy | 4 | Front-End Developer | 2 | 5 |  | Final design form for mainpage
Printsan | Çağla Çöpürkaya | 4 | Tester | 2 | 5 | Makes a meeting with customer for final design decisions and get all requirement infos. | Meeting with customer. | Helping Product Owner
Printsan | Ulaş Yılmaz | 4 | Back-end Developer | 2 | 2 | Database done with fake datas. Next week it will be ready with real data and has some dynamic API.
Printsan | Barış Baran Aslan | 4 | Back-end Developer | 2 | 2 |  | Database %80
Printsan | Abdullah Oranqaı | 4 | Analyst | 2 | 3 | Do the database analyze report.Do design writing report's analyze for both backend and frontend. Also take the infos from Elif and save them. If developers need anything or have questions, Abdullah will help them clearly. | Database Analyze Report
Printsan | Elif Meriç | 5 | Product Owner | 3 | 3 | Keep in contact with customer.Helps for the Jira problems for our team. We need premium account but Elif solve with remove one of our backend developers. We are always in a communication so that's not a problem for the team. |  | Report Helping
Printsan | Kadir Batuhan Demir | 5 | Product Manager | 3 | 3 | Preparing Excel documents and decide deliverable objects. Helped for some Slider design ideas.Decide meetings and keep in contact all team members |  | Design Analyze Helping
Printsan | Muratcan Tüfekçi | 5 | Front-End Developer | 15 | 10 | Slider,mission/vision,videoclip,footer,populer products parts are done. Also "Hakkımızda" part with certificates is done.Team part's general design is ready. Politicies,videoclip designs will be revised.
Printsan | Muhammet Aksoy | 5 | Front-End Developer | 15 | 10 |  |  | Design Analyze Helping
Printsan | Çağla Çöpürkaya | 5 | Tester | 5 | 5 | Start the test scenerios and save them in excel file. Make observations in developments and errors. Have usefull ideas for design problems. | testcaseforfrontend_5
Printsan | Ulaş Yılmaz | 5 | Back-end Developer | 15 | 10 | They have Corse Error and not resolved yet. But Front development is keep going. API and data's are in full condition
Printsan | Barış Baran Aslan | 5 | Back-end Developer | 15 | 10
Printsan | Abdullah Oranqaı | 5 | Analyst | 3 | 3 | Working on our Backlog revision for Jira for easy use. He keeps all needing for the backend and help frontend for designs.
Printsan | Elif Meriç | 6 | Product Owner | 5 | 2.5 | Make a meeting with customer and shows sites last updates. For Process part and Infrustructure(machine parkour) decides some photos with Printsan. Also choose icons for Team/Department info part and prepare MOV part on the report. | MOV part on the report | Helping Product Manager
Printsan | Kadir Batuhan Demir | 6 | Product Manager | 5 | 8 | Keep going filling the reports and decisions for meetings and sprints.Also prepare the Process text information because Printsan did not send them yet.After the preparation, we get pictures with Product Owner from Printsan and send them to Developers. | üretimlerv4 | Reporting
Printsan | Muratcan Tüfekçi | 6 | Front-End Developer | 5 | 3 | Made small revisions for videoclip and politicies parts.Change a photo from slider and change writing designs.General look is better now. After Process informations, our static Process page is done.
Printsan | Muhammet Aksoy | 6 | Front-End Developer | 5 | 3
Printsan | Çağla Çöpürkaya | 6 | Tester | 5 | 2.5 | Keep following the development phases on Github.Always communicate with developers because sometimes there can be problems from Github or testing information.Keeps going testings and reporting them. | testcaseforall_6
Printsan | Ulaş Yılmaz | 6 | Back-end Developer | 5 | 2.5 | Solve the Corse error and make some updates on database.They are ready for new API'.
Printsan | Barış Baran Aslan | 6 | Back-end Developer | 5 | 2.5
Printsan | Abdullah Oranqaı | 6 | Analyst | 5 | 3 | Backlog revision is done and really usefull on Jira. Keep developers needings for necessery times.
Printsan | Elif Meriç | 7 | Product Owner | 3 | 3 | Keep going on communication with the customer
Printsan | Kadir Batuhan Demir | 7 | Product Manager | 3 | 3 | Keep going on reporting
Printsan | Muratcan Tüfekçi | 7 | Front-End Developer | 8 | 6 | They done all of pages(Makine parkuru, Medya, İlanlar,Başvuru Formu) except Media Part. Media part need a new design. Project is nearly done.
Printsan | Muhammet Aksoy | 7 | Front-End Developer | 8 | 6
Printsan | Çağla Çöpürkaya | 7 | Tester | 3 | 4 | Keep going on testing | testcaseforall_7
Printsan | Ulaş Yılmaz | 7 | Back-end Developer | 3 | 3 | They arranged the informations in database and API's
Printsan | Barış Baran Aslan | 7 | Back-end Developer | 3 | 3
Printsan | Abdullah Oranqaı | 7 | Analyst | 3 | 0 | Because of the illness; he rested.
Printsan | Elif Meriç | 8 | Product Owner | 5 | 2.5 | Do a meeting with Prints for a bargain. But we didn't agree. Because of this, our project will not use in life. We quit some features and we will do some
Printsan | Kadir Batuhan Demir | 8 | Product Manager | 5 | 2.5
Printsan | Muratcan Tüfekçi | 8 | Front-End Developer | 5 | 2.5 | Bargaining and waiting for results. After the negative conversation, some features were deleted and the project slowed down. There is no need for so much effort now.
Printsan | Muhammet Aksoy | 8 | Front-End Developer | 5 | 2.5
Printsan | Çağla Çöpürkaya | 8 | Tester | 5 | 2.5
Printsan | Ulaş Yılmaz | 8 | Back-end Developer | 5 | 2.5
Printsan | Barış Baran Aslan | 8 | Back-end Developer | 5 | 2.5
Printsan | Abdullah Oranqaı | 8 | Analyst | 5 | 2.5 | Done Frontend Analysis report. | Frontend Analysis
Printsan | Elif Meriç | 9 | Product Owner | 1 | 1 | Reported review for possible problems and made MOV table final form. | MOV Table in Final Report | Checking paper works
Printsan | Kadir Batuhan Demir | 9 | Product Manager | 2 | 2 | Weekly Excel, Jira and Final Report filled
Printsan | Muratcan Tüfekçi | 9 | Front-End Developer | 5 | 1 | Done the responsive design for big screens with little revisions.Thought about Media tab
Printsan | Muhammet Aksoy | 9 | Front-End Developer | 5 | 1
Printsan | Çağla Çöpürkaya | 9 | Tester | 0 | 0 | Waited for final version
Printsan | Ulaş Yılmaz | 9 | Back-end Developer | 1.5 | 1.5 | General database and backend optimization
Printsan | Barış Baran Aslan | 9 | Back-end Developer | 1.5 | 1.5
Printsan | Abdullah Oranqaı | 9 | Analyst | 1 | 1 | Design ideas for Media tab |  | Helping Frontend
Printsan | Elif Meriç | 10 | Product Owner | 0.5 | 0.5 | Controlled the excel documents |  | Checking final reports and excels
Printsan | Kadir Batuhan Demir | 10 | Product Manager | 2.5 | 2.5 | Final excel documents done | Printsan_Report Project_Printsan_Final | Done the reporting
Printsan | Muratcan Tüfekçi | 10 | Front-End Developer | 10 | 10 | Admin panel and final form of website done
Printsan | Muhammet Aksoy | 10 | Front-End Developer | 10 | 10
Printsan | Çağla Çöpürkaya | 10 | Tester | 5 | 5 | Final tests and documents are done | testcaseforall_8
Printsan | Ulaş Yılmaz | 10 | Back-end Developer | 2 | 2 | Done final API's for admin panel
Printsan | Barış Baran Aslan | 10 | Back-end Developer | 2 | 2
Printsan | Abdullah Oranqaı | 10 | Analyst | 1 | 1 | Helped for Media tab
Printsan | Elif Meriç | 11 | Product Owner | 10 | 10 | Final checks on documents and re-arrengements on Fizibilite Report |  | Checking final reports and excels
Printsan | Kadir Batuhan Demir | 11 | Product Manager | 5 | 5 | Final preparations for the delivery | Printsan_Report Project_Printsan_Final HowtoOpen | Done the reporting
Printsan | Muratcan Tüfekçi | 11 | Front-End Developer | 10 | 10 | Final bugs fixed and admin panel's latest version is done
Printsan | Muhammet Aksoy | 11 | Front-End Developer | 10 | 10
Printsan | Çağla Çöpürkaya | 11 | Tester | 5 | 5 | Final tests are done | testcaseforall_final
Printsan | Ulaş Yılmaz | 11 | Back-end Developer | 2 | 2 | Testing datas were deleted and Contact Form service is written
Printsan | Barış Baran Aslan | 11 | Back-end Developer | 2 | 2
Printsan | Abdullah Oranqaı | 11 | Analyst | 4 | 4 | Re-arrengments on documents

## MeetingAttendance
Meeting | Team Member | Time | Present (Yes/No) | Duration
Project Planning | Elif Meriç | 1:00 | Yes | 1:00
Project Planning | Kadir Batuhan Demir | 1:00 | Yes | 1:00
Project Planning | Muratcan Tüfekçi | 1:00 | Yes | 1:00
Project Planning | Muhammet Aksoy | 1:00 | Yes | 1:00
Project Planning | Çağla Çöpürkaya | 1:00 | Yes | 1:00
Project Planning | Ulaş Yılmaz | 1:00 | Yes | 1:00
Project Planning | Barış Baran Aslan | 1:00 | Yes | 1:00
Project Planning | Abdullah Oranqaı | 1:00 | Yes | 1:00
Information Exchange about Product Backlog | Elif Meriç | 1:00 | Yes | 0:30
Information Exchange about Product Backlog | Kadir Batuhan Demir | 1:00 | Yes | 0:30
Project Design and Functional Decision | Elif Meriç | 2:30 | Yes | 2:30
Project Design and Functional Decision | Kadir Batuhan Demir | 2:30 | Yes | 2:30
Project Design and Functional Decision | Muratcan Tüfekçi | 2:30 | Yes | 2:30
Project Design and Functional Decision | Muhammet Aksoy | 2:30 | Yes | 2:30
Project Design and Functional Decision | Çağla Çöpürkaya | 2:30 | Yes | 2:30
Project Design and Functional Decision | Abdullah Oranqaı | 2:30 | Yes | 2:30
Project Design and Functional Decision | Ulaş Yılmaz | 2:30 | Yes | 2:30
Project Design and Functional Decision | Barış Baran Aslan | 2:30 | Yes | 2:30
Feasibility Report Preparation | Çağla Çöpürkaya | 2:30 | Yes | 2:30
Feasibility Report Preparation | Elif Meriç | 2:30 | Yes | 2:30
Feasibility Report Preparation | Abdullah Oranqaı | 2:30 | Yes | 2:30
Daily Meeting | Elif Meriç | 0:15 | Yes | 0:15
Daily Meeting | Kadir Batuhan Demir | 0:15 | Yes | 0:15
Daily Meeting | Muratcan Tüfekçi | 0:15 | Yes | 0:15
Daily Meeting | Muhammet Aksoy | 0:15 | Yes | 0:15
Daily Meeting | Çağla Çöpürkaya | 0:15 | Yes | 0:15
Daily Meeting | Ulaş Yılmaz | 0:15 | Yes | 0:15
Daily Meeting | Barış Baran Aslan | 0:15 | Yes | 0:15
Daily Meeting | Abdullah Oranqaı | 0:15 | Yes | 0:15
Database Design Decision | Elif Meriç | 0:30 | Yes | 0:10
Database Design Decision | Kadir Batuhan Demir | 0:30 | Yes | 0:10
Database Design Decision | Muratcan Tüfekçi | 0:30 | Yes | 0:10
Database Design Decision | Muhammet Aksoy | 0:30 | Yes | 0:10
Database Design Decision | Çağla Çöpürkaya | 0:30 | Yes | 0:10
Database Design Decision | Ulaş Yılmaz | 0:30 | Yes | 0:10
Database Design Decision | Barış Baran Aslan | 0:30 | Yes | 0:10
Database Design Decision | Abdullah Oranqaı | 0:30 | Yes | 0:10
Weekly Sprint Meeting | Elif Meriç | 0:20 | Yes | 0:20
Weekly Sprint Meeting | Kadir Batuhan Demir | 0:20 | Yes | 0:20
Weekly Sprint Meeting | Muratcan Tüfekçi | 0:20 | Yes | 0:20
Weekly Sprint Meeting | Muhammet Aksoy | 0:20 | Yes | 0:20
Weekly Sprint Meeting | Çağla Çöpürkaya |  | No
Weekly Sprint Meeting | Ulaş Yılmaz | 0:20 | Yes | 0:20
Weekly Sprint Meeting | Barış Baran Aslan | 0:20 | Yes | 0:20
Weekly Sprint Meeting | Abdullah Oranqaı |  | No
Customer Requests Meeting | Elif Meriç | 0:30 | Yes | 0:30
Customer Requests Meeting | Kadir Batuhan Demir | 0:30 | Yes | 0:30
Customer Requests Meeting | Muratcan Tüfekçi | 0:30 | Yes | 0:30
Customer Requests Meeting | Muhammet Aksoy | 0:30 | Yes | 0:30
Customer Requests Meeting | Çağla Çöpürkaya | 0:30 | Yes | 0:30
Customer Requests Meeting | Ulaş Yılmaz | 0:30 | Yes | 0:30
Customer Requests Meeting | Barış Baran Aslan | 0:30 | Yes | 0:30
Customer Requests Meeting | Abdullah Oranqaı | 0:30 | Yes | 0:30
Weekly Sprint Meeting-3 | Elif Meriç | 0:30 | Yes | 0:30
Weekly Sprint Meeting-3 | Kadir Batuhan Demir | 0:30 | Yes | 0:30
Weekly Sprint Meeting-3 | Muratcan Tüfekçi | 0:30 | Yes | 0:30
Weekly Sprint Meeting-3 | Muhammet Aksoy | 0:30 | Yes | 0:30
Weekly Sprint Meeting-3 | Çağla Çöpürkaya | 0:30 | Yes | 0:30
Weekly Sprint Meeting-3 | Ulaş Yılmaz | 0:30 | Yes | 0:30
Weekly Sprint Meeting-3 | Barış Baran Aslan | 0:30 | Yes | 0:30
Weekly Sprint Meeting-2 | Abdullah Oranqaı | 0:30 | Yes | 0:30
Customer Request Meeting | Elif Meriç | 2:00 | Yes | 2:00
Customer Request Meeting | Çağla Çöpürkaya | 2:00 | Yes | 2:00
Showing Design to Customer Meeting | Elif Meriç | 0:10 | Yes | 0:10
Showing Design to Customer Meeting | Kadir Batuhan Demir | 0:10 | Yes | 0:10
Showing Design to Customer Meeting | Muhammet Aksoy | 0:10 | Yes | 0:10
Showing Design to Customer Meeting | Abdullah Oranqaı | 0:10 | Yes | 0:10
Final Design Meeting | Elif Meriç | 0:30 | Yes | 0:30
Final Design Meeting | Kadir Batuhan Demir | 0:30 | Yes | 0:30
Final Design Meeting | Muratcan Tüfekçi | 0:30 | Yes | 0:30
Final Design Meeting | Muhammet Aksoy | 0:30 | Yes | 0:30
Final Design Meeting | Çağla Çöpürkaya | 0:30 | Yes | 0:30
Final Design Meeting | Ulaş Yılmaz | 0:30 | Yes | 0:30
Final Design Meeting | Barış Baran Aslan | 0:30 | Yes | 0:30
Final Design Meeting | Abdullah Oranqaı | 0:30 | Yes | 0:30
Weekly Sprint Meeting-4 | Elif Meriç | 1:00 | Yes | 1:00
Weekly Sprint Meeting-4 | Kadir Batuhan Demir | 1:00 | Yes | 1:00
Weekly Sprint Meeting-4 | Muratcan Tüfekçi | 1:00 | Yes | 1:00
Weekly Sprint Meeting-4 | Muhammet Aksoy | 1:00 | Yes | 1:00
Weekly Sprint Meeting-4 | Çağla Çöpürkaya | 1:00 | Yes | 1:00
Weekly Sprint Meeting-4 | Ulaş Yılmaz | 1:00 | Yes | 1:00
Weekly Sprint Meeting-4 | Barış Baran Aslan | 1:00 | Yes | 1:00
Weekly Sprint Meeting-4 | Abdullah Oranqaı | 1:00 | Yes | 1:00
Cors Error Meeting | Muratcan Tüfekçi | 0:10 | Yes | 0:10
Cors Error Meeting | Muhammet Aksoy | 0:10 | Yes | 0:10
Cors Error Meeting | Ulaş Yılmaz | 0:10 | Yes | 0:10
Cors Error Meeting | Barış Baran Aslan | 0:10 | Yes | 0:10
Design Feedback Meeting | Elif Meriç | 0:30 | Yes | 0:30
Design Feedback Meeting | Kadir Batuhan Demir | 0:30 | Yes | 0:30
Design Feedback Meeting | Muratcan Tüfekçi | 0:30 | Yes | 0:30
Design Feedback Meeting | Muhammet Aksoy |  | No
Design Feedback Meeting | Çağla Çöpürkaya | 0:30 | Yes | 0:30
Design Feedback Meeting | Ulaş Yılmaz | 0:30 | Yes | 0:30
Design Feedback Meeting | Barış Baran Aslan |  | No
Design Feedback Meeting | Abdullah Oranqaı | 0:30 | Yes | 0:30
Weekly Sprint Meeting-5 | Elif Meriç | 1:00 | Yes | 1:00
Weekly Sprint Meeting-5 | Kadir Batuhan Demir | 1:00 | Yes | 1:00
Weekly Sprint Meeting-5 | Muratcan Tüfekçi | 1:00 | Yes | 1:00
Weekly Sprint Meeting-5 | Muhammet Aksoy | 1:00 | Yes | 1:00
Weekly Sprint Meeting-5 | Çağla Çöpürkaya | 1:00 | Yes | 1:00
Weekly Sprint Meeting-5 | Ulaş Yılmaz | 1:00 | Yes | 1:00
Weekly Sprint Meeting-5 | Barış Baran Aslan | 1:00 | Yes | 1:00
Weekly Sprint Meeting-5 | Abdullah Oranqaı | 1:00 | Yes | 1:00
Daily Feedback Meeting | Elif Meriç | 0:30 | Yes | 0:30
Daily Feedback Meeting | Kadir Batuhan Demir | 0:30 | Yes | 0:30
Daily Feedback Meeting | Muratcan Tüfekçi | 0:30 | Yes | 0:30
Daily Feedback Meeting | Muhammet Aksoy | 0:30 | Yes | 0:30
Daily Feedback Meeting | Çağla Çöpürkaya | 0:30 | Yes | 0:30
Daily Feedback Meeting | Ulaş Yılmaz | 0:30 | No | 0:30
Daily Feedback Meeting | Barış Baran Aslan | 0:30 | No | 0:30
Daily Feedback Meeting | Abdullah Oranqaı | 0:30 | Yes | 0:30
Customer Meeting with Printsan | Elif Meriç | 2:00 | Yes | 2:00
| Printsan | 2:00 | Yes | 2:00
Weekly Sprint Meeting-6 | Elif Meriç | 1:00 | Yes | 1:00
Weekly Sprint Meeting-6 | Kadir Batuhan Demir | 1:00 | Yes | 1:00
Weekly Sprint Meeting-6 | Muratcan Tüfekçi | 1:00 | Yes | 1:00
Weekly Sprint Meeting-6 | Muhammet Aksoy | 1:00 | Yes | 1:00
Weekly Sprint Meeting-6 | Çağla Çöpürkaya | 1:00 | Yes | 1:00
Weekly Sprint Meeting-6 | Ulaş Yılmaz | 1:00 | Yes | 1:00
Weekly Sprint Meeting-6 | Barış Baran Aslan | 1:00 | Yes | 1:00
Weekly Sprint Meeting-6 | Abdullah Oranqaı | 1:00 | Yes | 1:00
Daily Feedback Meeting | Elif Meriç | 0:30 | Yes | 0:30
Daily Feedback Meeting | Kadir Batuhan Demir | 0:30 | Yes | 0:30
Daily Feedback Meeting | Muratcan Tüfekçi | 0:30 | Yes | 0:30
Daily Feedback Meeting | Muhammet Aksoy | 0:30 | Yes | 0:30
Daily Feedback Meeting | Çağla Çöpürkaya | 0:30 | Yes | 0:30
Daily Feedback Meeting | Ulaş Yılmaz | 0:30 | No | 0:30
Daily Feedback Meeting | Barış Baran Aslan | 0:30 | Yes | 0:30
Daily Feedback Meeting | Abdullah Oranqaı | 0:30 | Yes | 0:30
Design Feedback Meeting | Elif Meriç | 0:30 | Yes | 0:30
Design Feedback Meeting | Kadir Batuhan Demir | 0:30 | Yes | 0:30
Design Feedback Meeting | Muratcan Tüfekçi | 0:30 | Yes | 0:30
Design Feedback Meeting | Muhammet Aksoy | 0:30 | Yes | 0:30
Design Feedback Meeting | Çağla Çöpürkaya | 0:30 | Yes | 0:30
Design Feedback Meeting | Ulaş Yılmaz | 0:30 | No | 0:30
Design Feedback Meeting | Barış Baran Aslan | 0:30 | Yes | 0:30
Design Feedback Meeting | Abdullah Oranqaı | 0:30 | Yes | 0:30
Weekly Sprint Meeting-7 | Elif Meriç | 1:00 | Yes | 1:00
Weekly Sprint Meeting-7 | Kadir Batuhan Demir | 1:00 | Yes | 1:00
Weekly Sprint Meeting-7 | Muratcan Tüfekçi | 1:00 | Yes | 1:00
Weekly Sprint Meeting-7 | Muhammet Aksoy | 1:00 | Yes | 1:00
Weekly Sprint Meeting-7 | Çağla Çöpürkaya | 1:00 | Yes | 1:00
Weekly Sprint Meeting-7 | Ulaş Yılmaz | 1:00 | Yes | 1:00
Weekly Sprint Meeting-7 | Barış Baran Aslan | 1:00 | Yes | 1:00
Weekly Sprint Meeting-7 | Abdullah Oranqaı | 1:00 | Yes | 1:00
Customer Meeting with Printsan | Elif Meriç | 1:00 | Yes | 1:00
Customer Meeting with Printsan | Kadir Batuhan Demir | 1:00 | Yes | 1:00
Weekly Sprint Meeting-8 | Elif Meriç | 1:00 | Yes | 1:00
Weekly Sprint Meeting-8 | Kadir Batuhan Demir | 1:00 | Yes | 1:00
Weekly Sprint Meeting-8 | Muratcan Tüfekçi | 1:00 | Yes | 1:00
Weekly Sprint Meeting-8 | Muhammet Aksoy | 1:00 | Yes | 1:00
Weekly Sprint Meeting-8 | Çağla Çöpürkaya | 1:00 | Yes | 1:00
Weekly Sprint Meeting-8 | Ulaş Yılmaz | 1:00 | Yes | 1:00
Weekly Sprint Meeting-8 | Barış Baran Aslan | 1:00 | Yes | 1:00
Weekly Sprint Meeting-8 | Abdullah Oranqaı | 1:00 | Yes | 1:00
Admin Panel Meeting | Muratcan Tüfekçi | 1:00 | Yes | 1:00
Admin Panel Meeting | Muhammet Aksoy | 1:00 | Yes | 1:00
Daily Meeting | Elif Meriç | 0:30 | Yes | 0:30
Daily Meeting | Kadir Batuhan Demir | 0:30 | Yes | 0:30
Daily Meeting | Muratcan Tüfekçi | 0:30 | Yes | 0:30
Daily Meeting | Muhammet Aksoy | 0:30 | Yes | 0:30
Daily Meeting | Çağla Çöpürkaya | 0:30 | Yes | 0:30
Daily Meeting | Ulaş Yılmaz | 0:30 | No | 0:30
Daily Meeting | Barış Baran Aslan | 0:30 | Yes | 0:30
Daily Meeting | Abdullah Oranqaı | 0:30 | Yes | 0:30
Weekly Sprint Meeting-9 | Elif Meriç | 0:45 | Yes | 0:45
Weekly Sprint Meeting-9 | Kadir Batuhan Demir | 0:45 | Yes | 0:45
Weekly Sprint Meeting-9 | Muratcan Tüfekçi | 0:45 | Yes | 0:45
Weekly Sprint Meeting-9 | Muhammet Aksoy | 0:45 | Yes | 0:45
Weekly Sprint Meeting-9 | Çağla Çöpürkaya | 0:45 | Yes | 0:45
Weekly Sprint Meeting-9 | Ulaş Yılmaz | 0:45 | Yes | 0:45
Weekly Sprint Meeting-9 | Barış Baran Aslan | 0:45 | Yes | 0:45
Weekly Sprint Meeting-9 | Abdullah Oranqaı | 0:45 | Yes | 0:45
Final Meeting | Elif Meriç | 0:45 | Yes | 0:45
Final Meeting | Kadir Batuhan Demir | 0:45 | Yes | 0:45
Final Meeting | Muratcan Tüfekçi | 0:45 | Yes | 0:45
Final Meeting | Muhammet Aksoy | 0:45 | Yes | 0:45
Final Meeting | Çağla Çöpürkaya | 0:45 | Yes | 0:45
Final Meeting | Ulaş Yılmaz | 0:45 | Yes | 0:45
Final Meeting | Barış Baran Aslan | 0:45 | Yes | 0:45
Final Meeting | Abdullah Oranqaı | 0:45 | Yes | 0:45
Test and Presentation Meeting | Elif Meriç | 1:00 | Yes | 1:00
Test and Presentation Meeting | Kadir Batuhan Demir | 1:00 | Yes | 1:00
Test and Presentation Meeting | Muratcan Tüfekçi | 1:00 | Yes | 1:00
Test and Presentation Meeting | Muhammet Aksoy | 1:00 | Yes | 1:00
Test and Presentation Meeting | Çağla Çöpürkaya | 1:00 | Yes | 1:00
Test and Presentation Meeting | Ulaş Yılmaz | 1:00 | Yes | 1:00
Test and Presentation Meeting | Barış Baran Aslan | 1:00 | Yes | 1:00
Test and Presentation Meeting | Abdullah Oranqaı | 1:00 | Yes | 1:00
Test and Presentation Meeting-2 | Elif Meriç | 1:00 | Yes | 1:00
Test and Presentation Meeting-2 | Kadir Batuhan Demir | 1:00 | Yes | 1:00
Test and Presentation Meeting-2 | Muratcan Tüfekçi | 1:00 | Yes | 1:00
Test and Presentation Meeting-2 | Muhammet Aksoy | 1:00 | Yes | 1:00
Test and Presentation Meeting-2 | Çağla Çöpürkaya | 1:00 | Yes | 1:00
Test and Presentation Meeting-2 | Ulaş Yılmaz | 1:00 | Yes | 1:00
Test and Presentation Meeting-2 | Barış Baran Aslan | 1:00 | Yes | 1:00
Test and Presentation Meeting-2 | Abdullah Oranqaı | 1:00 | Yes | 1:00
Test and Presentation Meeting-3 | Elif Meriç | 1:00 | Yes | 1:00
Test and Presentation Meeting-3 | Kadir Batuhan Demir | 1:00 | Yes | 1:00
Test and Presentation Meeting-3 | Muratcan Tüfekçi | 1:00 | Yes | 1:00
Test and Presentation Meeting-3 | Muhammet Aksoy | 1:00 | Yes | 1:00
Test and Presentation Meeting-3 | Çağla Çöpürkaya | 1:00 | Yes | 1:00
Test and Presentation Meeting-3 | Ulaş Yılmaz | 1:00 | Yes | 1:00
Test and Presentation Meeting-3 | Barış Baran Aslan | 1:00 | Yes | 1:00
Test and Presentation Meeting-3 | Abdullah Oranqaı | 1:00 | Yes | 1:00

## ProjectDescription
Project Name | Project Description
Project Printsan | A professional website has been prepared with the latest technology for the Printsan Emprime company. It is aimed that the interface of this site is user-friendly, modern and aesthetic. With high visuality and simplicity, users will be able to find what they are looking for easily. At the same time, with the database and admin panel, the company will be able to keep the website up-to-date by updating the information it wants. In addition, new features such as "Job Application" and "Job Adversitement" have been added so that candidates can access job applications more quickly and easily.

## MOV
Team | Area of Impact | Impact | Value | Metric Type | Metric Definition | When | Current | Min | Expected | Aggressive | How to Measure
Printsan Emprime Website | Strategic | With new features ; the company will have more freedom to get new workers that they might be in need, as well as the costumers will have an easier and more flexible site to deal with, in addition to all these the users will be able to see the news of the company by using the media tab . | Increase reliability and the brand image of Printsan Emprime. | Percentage | Percentage of reliability and brand image | in 20 weeks | 60% | 50% | 95% | 5% | Evaluate the feedback the company has received since the start of use.
| User | Increase the number of audience addressed | Better and trustier UI. Turkish / English option. Eays job application. News blog. | Percentage | Percentage of audience addressed | in 12 weeks | 10% | 40% | 95% | 40% | Evaluate the user audience that the website addresses.
| Financial | Reduce the communication & total cost of scheduling | Reduce personnel & communication cost of scheduling. Reduce total cost of scheduling | Percentage | Reduce the percentage of personnel & communication cost of scheduling & Reduce the percentage of total cost of scheduling | in 8 months | 80% | 50% | 20% | 30% | Evaluate the current personel and communication costs, record ongoing costs of personel and communication and take the percentage & Evaluate the current cost of scheduling, record costs of scheduling and take the percentage at the end of 8 months
| Operational | Increase the company's reputation and interaction. | Recognize the popular items according to the sellings. Contact form. | Hours | Easier communication between company & user, and time is saved. | in 15 weeks | 10 Hours | 5 Hours | 1 Hour | 2 Hours | Evaluate how long the communication (response) between the user and the company takes.
| Social | Reduce the time that social media accounts are found by the user. | The news blog and the social media accounts are more easy to reach | Hours | The time spent by a user | in 10 weeks | 0.2 Hour | 0.1 Hour | 5 Minutes | 0.3 Hour | Evaluate the amount of time a potential user can spend on the website.
| MOV Statement | The Printsan Emprime website was designed with a simple and modern design, with the aim of increasing the prestige of the company by adding Turkish and English language options (cancelled) in order to show the professionalism of the company to a wider audience, besides, the operational parts of the website were designed effectively to save time.

## Scope
Scope | Product Backlog Item | Epic | Definition of Done
Functional | TR¦EN Option(cancel) |  | User can change the language.
Functional |  | Creating the admin panel | Admin will be able to control informations in the website.
Functional | Updating the brands(cancel) |  | The admin should be able to delete and add brands
Functional | Updating the new prints |  | The admin should be able to add or delete new or old print photos.
Functional | Updating popular products |  | The admin should be able to update the popular products
Functional | Updating the job advertisement |  | The admin should be able to update job advertisements
Functional | Updating the news(cancel) |  | The admin should be able to update the news about the factory.
Functional | Processes |  | Print processes are open in another page
Functional | Factory Infrastructure |  | Machine informations and photos beingg introduced.
Functional | Products menu tab |  | Open products page and show all of them
Functional | About Us Tab/Company History |  | Open new page and gives info about company.
Functional | Complaint Form |  | People can write their wishes or complaints, then send it to company
Functional | Listing the Company Policies |  | Policies open in a PDF.
Functional | Showing Number of Products Daily |  | Customers see daily products,worker numbers etc.
Functional |  | Company Profile | People know about Printsan's past and future targets.
Functional | Introduction about Company |  | Some written info and videos
Functional | Department Informations |  | Easy connection informations for different departments.
Functional | Certificates |  | Companies certificates are shown.
Functional | Virtual Tour |  | Customer can play and stop the videoclip.
Functional | Media tab |  | Interviews are in there.
Functional | Career Tab |  | People can see new candidates and send resumes.
Functional | The Factory Location on Map |  | In İletişim page ; there is a map.
Functional | Social Network Profiles |  | In footer; there are companies social media links.

## Responsibilities
Rules/Responsibility | Role
Each team member should work for the team tasks at least 75% of the hours decided. | Team Member
Team members should give the details of their work for each sprint planning meeting. | Team Member
Tasks should be clearly defined at the sprint planning meeting. | Team
The team should be able to generate enough tasks to utilize the whole team member's capacity | Team
The team should execute Product backlog grooming activities to fill the product backlog and refinement | P.Owner/P.Manager/Analyst
Project manager should define the project backlog, develop plans (schedule, communication, risk, resource) and make the arrangements the team to follow the plans | Project Manager
The project manager should collect the work of individuals, and update the reports every week. | Project Manager
Product owner should provide the product vision and roadmap | Product Owner
Product owner should provide the product backlog items in time and prioritize them | Product Owner
Scrum master should set the environment to maximize the productivity of the team and work to guarantee agile principles are applied | Scrum Master
Product owner and product manager should produce user stories from the backlog items for future planning. | P.Owner/P.Manager
Analyst should make revisions backlog items for easy development. | Analyst
Analysts and product owner should clarify the definiton of done for each of the user story (acceptance criteria) | Product Owner & Analyst
The analyst keeps all the information from the product owner and transmits it to the developers when necessary. Responsible for answering developers' questions about project content. | Analyst
Developers should develop the user stories taking care of definition of done (acceptance criteria) | Developers
Testers should generate test cases and test scenarios with expected and alternative paths to formally prove the satisfaction of DOD (Definition of Done) criteria | Tester
The Manager, collects the team logs, convert them to weekly, and prepare the final report. | Project Manager

## Technologies
Project Management
Agile | Jira,Slack
Planning | Meetings / Open Project / Screen Share / What are done part/ What will be done part / Design ideas from everyone / Requirements / Adding to Jira
Development Environment
Analysis & Design | Visual Paradigm , Microsoft Word
IDE | Visual Studio Code , Postman
DBMS | MsSql , SQL
Libraries | React-Router-Dom , Bootstrap , Styled Component
Framework: | React , Entity Framework
Code Management | GitHub
Languages | C# , JavaScript
Communication
Instant Messaging | WhatsApp
Voice call & TeamMeetings | Discord, MicrosoftTeams, Google Meetings

## EffortPlan
Activity(10 Weeks) | Weekly Hours | Weekly Minutes | Total Hours | Total Minutes | General %
Sprint planning | 1 | 60 | 10 | 600 | 57.1429
Daily Scrum | 0.2 | 12 | 2 | 120 | 11.4286
Sprint Review | 0.2 | 12 | 2 | 120 | 11.4286
Restrospective | 0.25 | 15 | 2.5 | 150 | 14.2857
Product backlog grooming | 0.1 | 6 | 1 | 60 | 5.7143
|  | General(11 Weeks) | 17.5 | 1050 | 100

## OtherResources
Title | Names & Explanations | Costs (TL)
Project Sponsor | Printsan Company is the owner of the projects and sponsor for the all of costs.
Project Manager | Kadir Batuhan Demir : Ran the project management and decided meetings. Done the first design analyses and some edits for the projects. Done the reporting, joined some meetings with the company. | 2000
Product Owner | Elif Meriç : Contacted the client always and learn "What they want?". Got informations in text,video,picture forms etc. Made presentations to client and got confirm in some processes.Helped the reporting. | 2000
Systems Analysts | Abdallah Oranqaı : Collected the data and delivered who needs them. Made analyze reports for easy to understand. Knew the all project and answered all questions in processes from developers. | 2000
Systems Tester | Çağla Çöpürkaya : After the project progressed a little, started the testing phases. Shared the problems and encountered with the team and contributed to the smooth progress with the solutions. Turned tests into a report. | 2000
Front-End Developers | Muratcan Tüfekçi & Muhammet Aksoy: Front-End developers. They coded design ideas and make the site responsive. They built most of the project. They used React, component based architecture.Always worked with Back-End developers coordinately. | 8000
Back-End Developers | Ulaş Yılmaz & Barış Baran Aslan: Back-End developers. They created the database and make API's. Also solved some errors. Always worked with Front-End developers coordinately. Used Entity Framework code first in creation of Database. Also used Postman in API. | 4000
Technical Infrastructure Team
Hardware | Kadir Batuhan Demir : MSI GE63VR 7RE Raider i7 GTX1060 Elif Meriç : Lenovo IdeaPad S340 15IWL Muratcan Tüfekçi : Lenovo v330-15ikb i5-8250u Muhammet Aksoy : Zalman z3 i5 4460 gtx960 8gb ram Barış Baran Aslan : Monster T7 21.8 i7-11800 RTX3070 Ulaş Yılmaz : HP Model15 i5-7thGen NVİDİA MX130 4GB Çağla Çöpürkaya : ASUS İ7 Nvidia GeForce MX250 16GB Abdallah Oranqai : Casper E600 i5 RTX 2060
Software | Front-End : Visual Studio Code, Github, Netlify Back-End : Visual Studio , MsSQL Managment Studio , Postman , FileZilla FTP Client , Godaddy Hosting , Plesk Server Managment Interface Test : Visual Studio Code , Katalon Studio
Facilities and Travel | We met at school every Saturday and made sprint plannings. Some of them used car, some of them used public transportation.
Total |  | 20000
Maintenance | Muratcan Tüfekçi | 1000

## WBS
Work Package: | Milestone | Phase | Phases | Deliverable | Milestone
Deployed Printsan Web-Site | Deployment of the Site | Phase 1: | Design and Planning | Feasibility Report | Feasibility Report finished.
|  | Phase 2: | Develop Project Charter & Plan | Project Charter and Plan | Project Charterand Plan is Published
|  | Phase 3: | Execute & Control | Developed Printsan Site | Completion of Implementation
|  | Phase 4: | Close the Project | Final Project Report | Project Accepted
|  | Phase | Activity/Task | Deliverable | Milestone
|  | Execute & Control | Analysis | Analysis Report | Analysis Completed
|  |  | Design | Design Report | Design is Completed
|  |  | Test Plan | Test Cases | Test Cases are Defined
|  |  | Implementation | Source Code of Implemented Site | Site is Implemented
|  |  | Testing | Test Results | Site is Tested

## AgileTeam
Role | Name(s) | # of People
Project Manager | Kadir Batuhan Demir | 1
Product Owner/SCRUM Master | Elif Meriç | 1
Developers | Muratcan Tüfekçi, Muhammet Aksoy, Ulaş Yılmaz, Barış Baran Aslan | 4
Analysts | Abdallah Oranqaı | 1
Testers | Çağla Çöpürkaya | 1
Total |  | 8

## Grading
Team | Team Member | Role | Deliverables | Effort (Total) | Personal Achievements | Self Rate (Out of 10) | Team's Rate (Average, Out of 10)
Printsan | Elif Meriç | Product Owner | FizibililiteReport, MovTable, ProductBacklog 1/2, Requirements | 36 hours | Learned and applied Agile methods, learned and used Jira as a project management tool, and Slack as a team collaboration tool, gained a real life experience as a product owner | 9 | 8.42
Printsan | Kadir Batuhan Demir | Product Manager | Design_WritingReport, ProductBacklog 1/2, Mockup, üretimlerv4, Report, Weekly Excels | 36,5 hours | Gain real-life experience , improvement on reporting skills , learn new Agile tools like Jira and Slack | 9 | 9.57
Printsan | Muratcan Tüfekçi | Front-End Developer |  | 56 hours | Learned how the agile project is managed in large teams and how teamwork should be, learned how to develop frontends with the React framework. | 10 | 9.57
Printsan | Muhammet Aksoy | Front-End Developer |  | 56 hours |  | 10 | 9
Printsan | Çağla Çöpürkaya | Tester | FizibiliteReport , testcaseforfrontend_5 , testcaseforall_6 , testcaseforall_7 , testcaseforall_8 , testcaseforall_final | 37,5 hours | Learned how to do nunit and xunit testing. Learned and applied how smoke and functional testing are done. The Katalon automation test tool was learned to use and applied to the project. Also, how to write test case reports was learned and applied. | 8 | 8.85
Printsan | Ulaş Yılmaz | Back-end Developer |  | 34 hours | Learned working with a large team and dividing working areas to accelerate development | 10 | 9.42
Printsan | Barış Baran Aslan | Back-end Developer |  | 34 hours |  | 10 | 9.28
Printsan | Abdullah Oranqaı | Analyst | FizibiliteReport , Database Analyze , Frontend Analysis , ProjectCharter , Printsan_BusinessCase | 26 hours | Experience, agile project method, analysing, reporting | 7 | 8.57