## Logs
Week | Team Member | Task | Duration (Minutes) | Duration (Hours)
1 | Elif Meriç | Elif find us a customer. Printsan is a textile company and needs a website. | 180 | 3
1 | Kadir Batuhan Demir | We do some researches for website ideas,themes. Make distribution of tasks. | 180 | 3
1 | Muratcan Tüfekçi |  | 180 | 3
1 | Muhammet Aksoy |  | 180 | 3
1 | Çağla Çöpürkaya |  | 180 | 3
1 | Ulaş Yılmaz |  | 180 | 3
1 | Barış Baran Aslan |  | 180 | 3
1 | Abdullah Oranqaı |  | 180 | 3
2 | Elif Meriç | Make meetings with customer and explain to us. Open a Jira and help for Feasibility Report. | 180 | 3
2 | Kadir Batuhan Demir | Planning for choosen theme and prepare Mock-ups for report and Front-End developers. | 180 | 3
2 | Muratcan Tüfekçi | Helps for Back-End table decisions. | 180 | 3
2 | Muhammet Aksoy | Helps for Back-End table decisions. | 180 | 3
2 | Çağla Çöpürkaya | Because of Feasibility Report experience, she is the main responsible. | 180 | 3
2 | Ulaş Yılmaz | Decide create tasks of tables. | 180 | 3
2 | Barış Baran Aslan | Decide create tasks of tables. | 180 | 3
2 | Abdullah Oranqaı | Design tables and make diagrams for the report. | 180 | 3
3 | Elif Meriç | Design decisions | 150 | 2.5
3 | Kadir Batuhan Demir |  | 150 | 2.5
3 | Muratcan Tüfekçi | Created most of the mainpage. | 150 | 2.5
3 | Muhammet Aksoy |  | 150 | 2.5
3 | Çağla Çöpürkaya | Prepare the projectcharter document. | 150 | 2.5
3 | Ulaş Yılmaz | Make database tables and connections on the MsSql | 150 | 2.5
3 | Barış Baran Aslan |  | 150 | 2.5
3 | Abdullah Oranqaı | Prepare the projectcharter document. | 150 | 2.5
4 | Elif Meriç | Makes a meeting with customer for final design decisions and get all requirement infos. | 300 | 5
4 | Kadir Batuhan Demir | Report updates and join conference with customer. Do detailed mock ups with design decisions and writing them as a report for developers. | 120 | 2
4 | Muratcan Tüfekçi | Main page design done with final form.Ready for dynamic data.Video clip and vision/mission designs will be revised. | 300 | 5
4 | Muhammet Aksoy |  | 300 | 5
4 | Çağla Çöpürkaya | Makes a meeting with customer for final design decisions and get all requirement infos. | 300 | 5
4 | Ulaş Yılmaz | Database done with fake datas. Next week it will be ready with real data and has some dynamic API. | 120 | 2
4 | Barış Baran Aslan |  | 120 | 2
4 | Abdullah Oranqaı | Do the database analyze report.Do design writing report's analyze for both backend and frontend. Also take the infos from Elif and save them. If developers need anything or have questions, Abdullah will help them clearly. | 180 | 3
5 | Elif Meriç | Keep in contact with customer.Helps for the Jira problems for our team. We need premium account but Elif solve with remove one of our backend developers. We are always in a communication so that's not a problem for the team. | 180 | 3
5 | Kadir Batuhan Demir | Preparing Excel documents and decide deliverable objects. Helped for some Slider design ideas.Decide meetings and keep in contact all team members | 180 | 3
5 | Muratcan Tüfekçi | Slider,mission/vision,videoclip,footer,populer products parts are done. Also "Hakkımızda" part with certificates is done.Team part's general design is ready. Politicies,videoclip designs will be revised. | 600 | 10
5 | Muhammet Aksoy |  | 600 | 10
5 | Çağla Çöpürkaya | Start the test scenerios and save them in excel file. Make observations in developments and errors. Have usefull ideas for design problems. | 300 | 5
5 | Ulaş Yılmaz | They have Corse Error and not resolved yet. But Front development is keep going. API and data's are in full condition | 600 | 10
5 | Barış Baran Aslan |  | 600 | 10
5 | Abdullah Oranqaı | Working on our Backlog revision for Jira for easy use. He keeps all needing for the backend and help frontend for designs. | 180 | 3
|  |  | 150 | 2.5
6 | Elif Meriç | Make a meeting with customer and shows sites last updates. For Process part and Infrustructure(machine parkour) decides some photos with Printsan. Also choose icons for Team/Department info part and prepare MOV part on the report. | 480 | 8
6 | Kadir Batuhan Demir | Keep going filling the reports and decisions for meetings and sprints.Also prepare the Process text information because Printsan did not send them yet.After the preparation, we get pictures with Product Owner from Printsan and send them to Developers. | 180 | 3
6 | Muratcan Tüfekçi | Made small revisions for videoclip and politicies parts.Change a photo from slider and change writing designs.General look is better now. After Process informations, our static Process page is done. | 180 | 3
6 | Muhammet Aksoy |  | 150 | 2.5
6 | Çağla Çöpürkaya | Keep following the development phases on Github.Always communicate with developers because sometimes there can be problems from Github or testing information.Keeps going testings and reporting them. | 150 | 2.5
6 | Ulaş Yılmaz | Solve the Corse error and make some updates on database.They are ready for new API'. | 150 | 2.5
6 | Barış Baran Aslan |  | 150 | 2.5
6 | Abdullah Oranqaı | Backlog revision is done and really usefull on Jira. Keep developers needings for necessery times. | 180 | 3
7 | Elif Meriç | Keep going on communication with the customer | 180 | 3
7 | Kadir Batuhan Demir | Keep going on reporting | 180 | 3
7 | Muratcan Tüfekçi | They done all of pages(Makine parkuru, Medya, İlanlar,Başvuru Formu) except Media Part. Media part need a new design. Project is nearly done. | 360 | 6
7 | Muhammet Aksoy |  | 360 | 6
7 | Çağla Çöpürkaya | Keep going on testing | 240 | 4
7 | Ulaş Yılmaz | They arranged the informations in database and API's | 180 | 3
7 | Barış Baran Aslan |  | 180 | 3
7 | Abdullah Oranqaı | Because of the illness; he rested. | 0 | 0
8 | Elif Meriç | Do a meeting with Prints for a bargain. But we didn't agree. Because of this, our project will not use in life. We quit some features and we will do some | 150 | 2.5
8 | Kadir Batuhan Demir |  | 150 | 2.5
8 | Muratcan Tüfekçi | Bargaining and waiting for results. After the negative conversation, some features were deleted and the project slowed down. There is no need for so much effort now. | 150 | 2.5
8 | Muhammet Aksoy |  | 150 | 2.5
8 | Çağla Çöpürkaya |  | 150 | 2.5
8 | Ulaş Yılmaz |  | 150 | 2.5
8 | Barış Baran Aslan |  | 150 | 2.5
8 | Abdullah Oranqaı | Done Frontend Analysis report. | 150 | 2.5
9 | Elif Meriç | Reported review for possible problems and made MOV table final form. | 60 | 1
9 | Kadir Batuhan Demir | Weekly Excel, Jira and Final Report filled | 120 | 2
9 | Muratcan Tüfekçi | Done the responsive design for big screens with little revisions.Thought about Media tab | 60 | 1
9 | Muhammet Aksoy |  | 60 | 1
9 | Çağla Çöpürkaya | Waited for final version | 0 | 0
9 | Ulaş Yılmaz | General database and backend optimization | 150 | 1.5
9 | Barış Baran Aslan |  | 150 | 1.5
9 | Abdullah Oranqaı | Design ideas for Media tab | 60 | 1
10 | Elif Meriç | Controlled the excel documents | 30 | 0.5
10 | Kadir Batuhan Demir | Final excel documents done | 150 | 2.5
10 | Muratcan Tüfekçi | Admin panel and final form of website done | 600 | 10
10 | Muhammet Aksoy |  | 600 | 10
10 | Çağla Çöpürkaya | Final tests and documents are done | 300 | 5
10 | Ulaş Yılmaz | Done final API's for admin panel | 120 | 2
10 | Barış Baran Aslan |  | 120 | 2
10 | Abdullah Oranqaı | Helped for Media tab | 60 | 1
11 | Elif Meriç | Final checks on documents and re-arrengements on Fizibilite Report | 600 | 10
11 | Kadir Batuhan Demir | Final preparations for the delivery | 300 | 5
11 | Muratcan Tüfekçi | Final bugs fixed and admin panel's latest version is done | 600 | 10
11 | Muhammet Aksoy |  | 600 | 10
11 | Çağla Çöpürkaya | Final tests are done | 300 | 5
11 | Ulaş Yılmaz | Testing datas were deleted and Contact Form service is written | 120 | 2
11 | Barış Baran Aslan |  | 120 | 2
11 | Abdullah Oranqaı | Re-arrengments on documents | 240 | 4
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
2
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
3
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
4
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
6
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7
7

## WeekWork
Week | Member | Role | Expected Workin Hours | Actual Worked Hours | Missing Hours | Week Actual vs Planned Work Ratio
1 | Elif Meriç | Product Owner | 3 | 3 | 0 | 100%
1 | Kadir Batuhan Demir | Project Manager | 3 | 3 | 0 | 100%
1 | Muratcan Tüfekçi | Front-End Dev | 3 | 3 | 0 | 100%
1 | Muhammet Aksoy | Front-End Dev | 3 | 3 | 0 | 100%
1 | Çağla Çöpürkaya | Tester | 3 | 3 | 0 | 100%
1 | Ulaş Yılmaz | Back-End Developer | 3 | 3 | 0 | 100%
1 | Barış Baran Aslan | Database | 3 | 3 | 0 | 100%
1 | Abdullah Oranqaı | Analyst | 3 | 3 | 0 | 100%
2 | Elif Meriç | Product Owner | 3 | 3 | 0 | 100%
2 | Kadir Batuhan Demir | Project Manager | 3 | 3 | 0 | 100%
2 | Muratcan Tüfekçi | Front-End Dev | 3 | 3 | 0 | 100%
2 | Muhammet Aksoy | Front-End Dev | 3 | 3 | 0 | 100%
2 | Çağla Çöpürkaya | Tester | 3 | 3 | 0 | 100%
2 | Ulaş Yılmaz | Back-End Developer | 3 | 3 | 0 | 100%
2 | Barış Baran Aslan | Database | 3 | 3 | 0 | 100%
2 | Abdullah Oranqaı | Analyst | 3 | 3 | 0 | 100%
3 | Elif Meriç | Product Owner | 3.5 | 2.5 | 1 | 71.43%
3 | Kadir Batuhan Demir | Project Manager | 3.5 | 2.5 | 1 | 71.43%
3 | Muratcan Tüfekçi | Front-End Dev | 3.5 | 2.5 | 1 | 71.43%
3 | Muhammet Aksoy | Front-End Dev | 3.5 | 2.5 | 1 | 71.43%
3 | Çağla Çöpürkaya | Tester | 3.5 | 2.5 | 1 | 71.43%
3 | Ulaş Yılmaz | Back-End Developer | 3.5 | 2.5 | 1 | 71.43%
3 | Barış Baran Aslan | Database | 3.5 | 2.5 | 1 | 71.43%
3 | Abdullah Oranqaı | Analyst | 3.5 | 2.5 | 1 | 71.43%
#DIV/0!
4 | Elif Meriç | Product Owner | 2 | 5 | 0 | 250%
4 | Kadir Batuhan Demir | Project Manager | 2 | 2 | 0 | 100%
4 | Muratcan Tüfekçi | Front-End Dev | 2 | 5 | 0 | 250%
4 | Muhammet Aksoy | Front-End Dev | 2 | 5 | 0 | 250%
4 | Çağla Çöpürkaya | Tester | 2 | 5 | 0 | 250%
4 | Ulaş Yılmaz | Back-End Developer | 2 | 2 | 0 | 100%
4 | Barış Baran Aslan | Database | 2 | 2 | 0 | 100%
4 | Abdullah Oranqaı | Analyst | 2 | 3 | 0 | 150%
#DIV/0!
5 | Elif Meriç | Product Owner | 3 | 3 | 0 | 100%
5 | Kadir Batuhan Demir | Project Manager | 3 | 3 | 0 | 100%
5 | Muratcan Tüfekçi | Front-End Dev | 15 | 10 | 5 | 66.67%
5 | Muhammet Aksoy | Front-End Dev | 15 | 10 | 5 | 66.67%
5 | Çağla Çöpürkaya | Tester | 5 | 5 | 0 | 100%
5 | Ulaş Yılmaz | Back-End Developer | 15 | 10 | 5 | 66.67%
5 | Barış Baran Aslan | Database | 15 | 10 | 5 | 66.67%
5 | Abdullah Oranqaı | Analyst | 3 | 3 | 0 | 100%
#DIV/0!
6 | Elif Meriç | Product Owner | 5 | 2.5 | 2.5 | 50%
6 | Kadir Batuhan Demir | Project Manager | 5 | 8 | 0 | 160%
6 | Muratcan Tüfekçi | Front-End Dev | 5 | 3 | 2 | 60%
6 | Muhammet Aksoy | Front-End Dev | 5 | 3 | 2 | 60%
6 | Çağla Çöpürkaya | Tester | 5 | 2.5 | 2.5 | 50%
6 | Ulaş Yılmaz | Back-End Developer | 5 | 2.5 | 2.5 | 50%
6 | Barış Baran Aslan | Database | 5 | 2.5 | 2.5 | 50%
6 | Abdullah Oranqaı | Analyst | 5 | 3 | 2 | 60%
#DIV/0!
7 | Elif Meriç | Product Owner | 3 | 3 | 0 | 100%
7 | Kadir Batuhan Demir | Project Manager | 3 | 3 | 0 | 100%
7 | Muratcan Tüfekçi | Front-End Dev | 8 | 6 | 0 | 75%
7 | Muhammet Aksoy | Front-End Dev | 8 | 6 | 0 | 75%
7 | Çağla Çöpürkaya | Tester | 3 | 4 | 0 | 133.3%
7 | Ulaş Yılmaz | Back-End Developer | 3 | 3 | 0 | 100%
7 | Barış Baran Aslan | Database | 3 | 3 | 0 | 100%
7 | Abdullah Oranqaı | Analyst | 3 | 0 | 3 | 0%
8 | Elif Meriç | Product Owner | 5 | 2.5 | 2.5 | 50%
8 | Kadir Batuhan Demir | Project Manager | 5 | 2.5 | 2.5 | 50%
8 | Muratcan Tüfekçi | Front-End Dev | 5 | 2.5 | 2.5 | 50%
8 | Muhammet Aksoy | Front-End Dev | 5 | 2.5 | 2.5 | 50%
8 | Çağla Çöpürkaya | Tester | 5 | 2.5 | 2.5 | 50%
8 | Ulaş Yılmaz | Back-End Developer | 5 | 2.5 | 2.5 | 50%
8 | Barış Baran Aslan | Database | 5 | 2.5 | 2.5 | 50%
8 | Abdullah Oranqaı | Analyst | 5 | 2.5 | 2.5 | 50%
9 | Elif Meriç | Product Owner | 1 | 1 | 1 | 100%
9 | Kadir Batuhan Demir | Project Manager | 2 | 2 | 0 | 100%
9 | Muratcan Tüfekçi | Front-End Dev | 5 | 1 | 4 | 20%
9 | Muhammet Aksoy | Front-End Dev | 5 | 1 | 4 | 20%
9 | Çağla Çöpürkaya | Tester | 0 | 0 | 0 | #DIV/0!
9 | Ulaş Yılmaz | Back-End Developer | 1.5 | 1.5 | 0 | 100%
9 | Barış Baran Aslan | Database | 1.5 | 1.5 | 0 | 100%
9 | Abdullah Oranqaı | Analyst | 1 | 1 | 1 | 100%
10 | Elif Meriç | Product Owner | 0.5 | 0.5 | 0 | 100%
10 | Kadir Batuhan Demir | Project Manager | 2.5 | 2.5 | 0 | 100%
10 | Muratcan Tüfekçi | Front-End Dev | 10 | 10 | 0 | 100%
10 | Muhammet Aksoy | Front-End Dev | 10 | 10 | 0 | 100%
10 | Çağla Çöpürkaya | Tester | 5 | 5 | 0 | 100%
10 | Ulaş Yılmaz | Back-End Developer | 2 | 2 | 0 | 100%
10 | Barış Baran Aslan | Database | 2 | 2 | 0 | 100%
10 | Abdullah Oranqaı | Analyst | 1 | 1 | 0 | 100%
11 | Elif Meriç | Product Owner | 10 | 10 | 0 | 100%
11 | Kadir Batuhan Demir | Project Manager | 5 | 5 | 0 | 100%
11 | Muratcan Tüfekçi | Front-End Dev | 10 | 10 | 0 | 100%
11 | Muhammet Aksoy | Front-End Dev | 10 | 10 | 0 | 100%
11 | Çağla Çöpürkaya | Tester | 5 | 5 | 0 | 100%
11 | Ulaş Yılmaz | Back-End Developer | 2 | 2 | 0 | 100%
11 | Barış Baran Aslan | Database | 2 | 2 | 0 | 100%
11 | Abdullah Oranqaı | Analyst | 4 | 4 | 0 | 100%

## SemesterReport
Member | Role | Time to Leave | Planned Hours for the Hours | Actual Hours for Semester | Missing Hours | Actual vs Planned Ratio for Semester | Team Summary for Semester | Values
Elif Meriç | Product Owner | 2022-01-01 | 40 | 36 | 7 | 90% | Planned Hours | 320
Kadir Batuhan Demir | Project Manager | 2022-01-01 | 40 | 36.5 | 3.5 | 91.25% | Actual Hours | 316
Muratcan Tüfekçi | Front-End Developer | 2022-01-01 | 40 | 56 | 14.5 | 140% | Missing Hours | 77
Muhammet Aksoy | Front-End Developer | 2022-01-01 | 40 | 56 | 14.5 | 140% | Actual vs Planned Hours Ratio | 98.75%
Çağla Çöpürkaya | Tester | 2022-01-01 | 40 | 37.5 | 6 | 93.75%
Ulaş Yılmaz | Back-End Developer | 2022-01-01 | 40 | 34 | 11 | 85%
Barış Baran Aslan | Database | 2022-01-01 | 40 | 34 | 11 | 85%
Abdullah Oranqaı | Analyst | 2022-01-01 | 40 | 26 | 9.5 | 65%

## ProductBacklog
PBI Number | PBI Type | Name | Explanation | Roadmap | Week | User Story | Requirement | Test Case | Developed | Tested
1 | Feature(Cancelled) | TR¦EN Option | There will be 2 languages options for users. |  |  | As an customer, I want to get information in English too because English is international.
2 | Expectatition | Both of Turkish and English languages should be provided in the website. | Users may be foreign, so the website should be serve in English and Turkish.
3 | Requirement | Methods for providing different languages | For the website to be in two different languages, defined methods in .NET environment for different language support will be used. |  |  |  | Special methods.
1 | Epic | Creating the admin panel | The admin should access required pages to |  | 10th Week | As an owner, I want to control our informations and numbers because our arrengements,products, numbers etc. can be change so tat keep up date. | An admin panel with a database. | The view progress in direct proportion to what analysed? Is it possible to go to the admin section with" http://localhost:3000/Admin" link (admin login not created yet) | OK | OK(SUCCESS)
2 | Feature(Cancelled) | Updating the brands | The admin should be able to delete and add brands
3 | Feature | Updating the new prints | The admin should be able to add or delete new or old print photos. |  |  |  |  | The "Add new product" button is working? Do we get an error while editing the product? Any correct feedback get on the error? | OK | OK(SUCCESS)
4 | Feature(Cancelled) | Updating the department info | The admin should be able to update department informations.
5 | Feature | Updating the job advertisement | The admin should be able to update job advertisements |  |  |  |  | The view progress in direct proportion to what analysed?The "Ilan olustur" button is working? Do we get an error while adding the advertisement? Any correct feedback get on the error? Does it appear in the system when we adding? | OK | OK(SUCCESS)
6 | Feature(Cancelled) | Updating the news | The admin should be able to update the news about the factory.
12 | Feature | Processes and laboratory | Manufacturing processes (printing, sewing, washing, quality control, etc.) should be located on the site. |  | 5th Week | As an customer, I want to learn print and laboratuary processes for my curiosity. | Processes explanations and laboratuary informations. | Do you go to the statically incoming print processes link? Is the process display in the correct order? Is there something wrong with your appearance? Are the production processes made with the analyzed correct? Does it fit the customer view? | OK | OK(SUCCESS)
13 | Expectatition | Customers can read print processes and laboratory. | There are lot of steps for paintings. If customers or just visiters curious about them ; processes can be readible in a clean and simple way. |  |  | . | . | The view progress in direct proportion to what was analyzed? What is the loading speed of the data? Is its appearance suitable for the customer? |  | OK(SUCCESS)
14 | Requirement | Simple design | Readers shouldnt be bored thats why simple design is important.
11 | Feature | Factory Infrastructure | The factory infrastructure e.g., machines, details about machines should be presented. |  | 6th Week | As an owner, I want to introduce our machines. | Machines details. | The view progress in direct proportion to what was analyzed? The video is working correctly? | OK | OK(SUCCESS)
12 | Feature | Products menu tab | The products should be listed under a menu tab, and their infos should be given in detail. |  | 5th Week |  | Product details and print variety descriptions. | The view detail progress in direct proportion to what was analyzed? | OK | OK(SUCCESS)
1 | Feature | Media tab | Company do interviews. |  | 6th Week | As an owner, I want to show our media news for our promotion. |  | The view progress in direct proportion to what was analyzed? The links are working correctly? | OK | OK(SUCCESS)
2 | Expectatition | Media moments should be seen | Company do interviews with newspapers and TV Channels. That shows success and people should be know it. |  |  |  |  | Is the media prepared in an explanatory way? | OK | OK(SUCCESS)
3 | Requirement | Company success and interviews | The company should provide their awards/successes.
1 | Feature | Compaint Form | The website contains a contact form to enable the users submit their wishes and complaints. |  | 6th Week | As an customer, I want to forward my requests and complaints to company basicly.So that company will know their positive and negative sides. | Forms with database connections.Also users some info's. | The view progress in direct proportion to what was analyzed? The links are working correctly? Are the data transmitted properly? | OK | OK(SUCCESS)
2 | Expectatition | Communication for requests and complaints. | Every people who has complaint or advices; can tell us. That is important for Company's development.
3 | Requirement | Users info's for feedbacks Saving in database. | Company should save forms and make improvements for them. Company maybe wants to send greeting messages for who writes the forms.
1 | Feature | Listing the Company Policies | Company wants to share policies for honesty. |  | 5th Week | As an owner, I want to show our company policies honestly so that customers can see our principles. | Policy papers in PDF. | Is the policy link accessible? Is the data coming from the database correctly? Do additional pdfs open without problems? Do all the principles appear correctly? Is it a customer appealing look? | OK | OK(SUCCESS)
2 | Expectatition | Publishing policies. | Company has policies like etics,enviromental policies etc. | [6 empty] | OK(SUCCESS)
3 | Requirement | Policy papers | For sharing we need papers but in a simple and clean sentences. | [6 empty] | OK(SUCCESS)
1 | Feature | Showing Number of Products Daily | Number of products producted per day, their daily amount (kg or ton), number of machines should be presented. |  | 4th Week | As an owner, I want to show our daily production numbers so that peopls knows our great production capacity. | Products,brands , employees numbers etc. | Can the dynamically displayed counter data be accessed from the database without any problems? Does the counter display look correct? Does incremental view work correctly on the page? | OK | OK(SUCCESS)
2 | Expectatition | Showing daily numbers | Show daily numbers in a small part in the WebSite | [6 empty] | OK(SUCCESS)
3 | Requirement | Numbers | Company has the numbers. | [6 empty] | OK(SUCCESS)
1 | Epic | Company Profile Tab | Company should be introduced to people ; who has curious to Printsan |  | 5th Week | As an owner, I want to give introductions about our company by this way we can introduce ourselves directly to our customers. | Company promotions,team members and certificate logos. | Are the about us and homepage links working correctly? Is there an accurate view of statically inserted data? Has the view coded with the analyzed view progressed in direct proportion? | OK | OK(SUCCESS)
2 | Expectatition | Introduction about Company | People should know about Company's past,now and future targets | [6 empty] | OK(SUCCESS)
3 | Requirement | Introduction Letter | Introduction letter is the best way. | [6 empty] | OK(SUCCESS)
4 | Feature | Department Information | Departments and their infos such as email, phone number, fax number should be presented. |  | 5th Week |  |  | Is it possible to access the statically incoming team information link? Is there an error in your view? Does it fit the customer view? | OK | OK(SUCCESS)
5 | Feature | Certificates | Certificates should be shown. |  | 5th Week | As an admin, I want to control and show our certificates easily so that keep up to date certificates. |  | Is the appearance of the certificate shown in the about us section directly proportional to the analyzed one? Are any errors encountered while accessing dynamically incoming data? Can pdfs be accessed when clicking on certificates? | OK | OK(SUCCESS)
1 | Feature | Virtual Tour | A video tour for visual company promotion |  | 5th Week |  | Videoclip. | Did the virtual tour video view progress in direct proportion to what was analysed? Does the video link work properly? Are you encountering any errors while accessing the video? | OK | OK(SUCCESS)
2 | Expectatition | Factory and office tour | People should see production part at the factory and see office hours too.
3 | Requirement | Video clip | Company should make a highlighted video clip.
1 | Feature | Career Tab | There should be a career tab to submit the resumes for new candidates to apply for a job to Printsan. |  | 6th Week | As an owner, I want to advertise for a job applys and accepts resumees so that I can find employees on my own site. | Submit CV part and job postings. | The view progress in direct proportion to what was analyzed? The links are working correctly? Does the application take place? Are the data transmitted properly? | OK | OK(SUCCESS)
2 | Feature | The Factory Location on Map | The factory location on the map should be presented. |  | 6th Week |  | Google Maps. |  |  | OK (SUCCESS)
1 | Feature | Social Network Profiles | Social network profiles such as Instagram, Facebook, YouTube should be located in the website. |  | 4th Week | As an customer, I want to follow social media accounts so that I can see Companies media side. | Social Network addresses. |  | OK | OK(SUCCESS)
2 | Requirement | Required profiles should be provided | Company social media profiles should be provided.
| Epic | Responsive Design | Site will be responsive for every screen. |  | 10th Week | As an user, I want to see all the site in my screen without visual errors. | Design | When the scale changes, does the appearance of the project deteriorate? | OK | OK(SUCCESS)

## UserStoryTask
FEATURE NO | FEATURE NAME | USER STORY | Analyst Name | Mockuper | Front-Ender | Back-Ender | Tester Name | Analyzed | Mockup OK | Test Case | Front-End OK | Back-End OK | Tested | Story Done?
Feature 1 | Updating the inspections made to the factory Cancelled | As an admin, I want to update inspections. So that I can control the inspection list. | Abdullah Oranqaı |  | Muratcan Tüfekçi & Muhammet Aksoy | Barış Baran Aslan & Ulaş Yılmaz | Çağla Çöpürkaya | OK |  | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled
Feature 2 | Updating the new prints(Dynamic) | As an admin, I want to add or delete new prints so that keep up to date. | Abdullah Oranqaı |  | Muratcan Tüfekçi & Muhammet Aksoy | Barış Baran Aslan & Ulaş Yılmaz | Çağla Çöpürkaya | OK |  | The "Add new product" button is working? Do we get an error while adding a new product? Any correct feedback get on the error? | OK | OK | OK(SUCCESS) | DONE
Feature 3 | Updating the brands(Dynamic) Cancelled | As an admin , I want to update brands for keep up to date. | Abdullah Oranqaı |  | Muratcan Tüfekçi & Muhammet Aksoy | Barış Baran Aslan & Ulaş Yılmaz | Çağla Çöpürkaya | OK |  | Cancelled | OK | OK but not in admin control | Cancelled | Cancelled
Feature 4 | TR ¦EN option Cancelled | As an customer, I want to get information in English too because English is international. |  |  | Muratcan Tüfekçi & Muhammet Aksoy | Barış Baran Aslan & Ulaş Yılmaz | Çağla Çöpürkaya |  |  | Cancelled | Cancelled | Cancelled | Cancelled | Cancelled
Feature 5 | Processes of the production(Static) | As an customer, I want to learn print processes for my curiosity. | Abdullah Oranqaı | Kadir Batuhan Demir | Muratcan Tüfekçi & Muhammet Aksoy | Barış Baran Aslan & Ulaş Yılmaz | Çağla Çöpürkaya | OK | OK | Do you go to the statically incoming print processes link? Is the process display in the correct order? Is there something wrong with your appearance? Are the production processes made with the analyzed correct? Does it fit the customer view? | OK | OK | OK(SUCCESS) | DONE
Feature 6 | Team information | As a owner , I want to give my department communication info's so that people can achieve which departmant they need. |  |  | Muratcan Tüfekçi & Muhammet Aksoy | Barış Baran Aslan & Ulaş Yılmaz | Çağla Çöpürkaya |  |  | Is it possible to access the statically incoming team information link? Is there an error in your view? Does it fit the customer view? | OK | OK | OK | DONE
Feature 7 | Machines(Dynamic) | As an owner, I want to introduce our machines. | Abdullah Oranqaı | Kadir Batuhan Demir | Muratcan Tüfekçi & Muhammet Aksoy | Barış Baran Aslan & Ulaş Yılmaz | Çağla Çöpürkaya | OK | OK | The view progress in direct proportion to what was analyzed? The video is working correctly? | OK | OK but not in admin control | OK(SUCCESS) | DONE
Feature 8 | Complaint form | As an customer, I want to forward my requests and complaints to company basicly.So that company will know their positive and negative sides. | Abdullah Oranqaı | Kadir Batuhan Demir | Muratcan Tüfekçi & Muhammet Aksoy | Barış Baran Aslan & Ulaş Yılmaz | Çağla Çöpürkaya | OK | OK | The view progress in direct proportion to what was analyzed? The links are working correctly? Are the data transmitted properly? | OK | OK | OK(SUCCESS) | DONE
Feature 9 | Listing the Company Policies(Dynamic) | As an owner, I want to show our company policies honestly so that customers can see our principles. | Abdullah Oranqaı | Kadir Batuhan Demir | Muratcan Tüfekçi & Muhammet Aksoy | Barış Baran Aslan & Ulaş Yılmaz | Çağla Çöpürkaya | OK | OK | Is the policy link accessible? Is the data coming from the database correctly? Do additional pdfs open without problems? Do all the principles appear correctly? Is it a customer appealing look? | OK | OK but not in admin control | OK(SUCCESS) | DONE
Feature 10 | Showing number of products per day(Dynamic) | As an owner, I want to show our daily production numbers so that peopls knows our great production capacity. | Abdullah Oranqaı | Kadir Batuhan Demir | Muratcan Tüfekçi & Muhammet Aksoy | Barış Baran Aslan & Ulaş Yılmaz | Çağla Çöpürkaya | OK | OK | Can the dynamically displayed counter data be accessed from the database without any problems? Does the counter display look correct? Does incremental view work correctly on the page? | OK | OK but not in admin control | OK(SUCCESS) | DONE
Feature 11 | Company Profile | As an owner, I want to give introductions about our company by this way we can introduce ourselves directly to our customers. | Abdullah Oranqaı | Kadir Batuhan Demir | Muratcan Tüfekçi & Muhammet Aksoy | Barış Baran Aslan & Ulaş Yılmaz | Çağla Çöpürkaya | OK | OK | Are the about us and homepage links working correctly? Is there an accurate view of statically inserted data? Has the view coded with the analyzed view progressed in direct proportion? | OK | OK | OK(SUCCESS) | DONE
Feature 12 | Virtual tour | As an owner, I want to show our facility and offices virtually so that people can see our working diciplines. | Abdullah Oranqaı | Kadir Batuhan Demir | Muratcan Tüfekçi & Muhammet Aksoy | Barış Baran Aslan & Ulaş Yılmaz | Çağla Çöpürkaya | OK | OK | Did the virtual tour video view progress in direct proportion to what was analysed? Does the video link work properly? Are you encountering any errors while accessing the video? | OK | OK | OK(SUCCESS) | DONE
Feature 13 | Media tab(Dynamic) | As an owner, I want to show our media news for our promotion. | Abdullah Oranqaı | Kadir Batuhan Demir | Muratcan Tüfekçi & Muhammet Aksoy | Barış Baran Aslan & Ulaş Yılmaz | Çağla Çöpürkaya | OK | OK | The view progress in direct proportion to what was analyzed? The links are working correctly? | OK | OK | OK(SUCCESS) | DONE
Feature 14 | Arrangement of the Certificates(Dynamic) Cancelled | As an admin, I want to control and show our certificates easily so that keep up to date certificates. | Abdullah Oranqaı | Kadir Batuhan Demir | Muratcan Tüfekçi & Muhammet Aksoy | Barış Baran Aslan & Ulaş Yılmaz | Çağla Çöpürkaya | OK | OK | Is the appearance of the certificate shown in the about us section directly proportional to the analyzed one? Are any errors encountered while accessing dynamically incoming data? Can pdfs be accessed when clicking on certificates? | OK | OK but not in admin control | OK(SUCCESS) | DONE
Feature 15 | Career Part(Dynamic) | As an owner, I want to advertise for a job applys and accepts resumees so that I can find employees on my own site. | Abdullah Oranqaı | Kadir Batuhan Demir | Muratcan Tüfekçi & Muhammet Aksoy | Barış Baran Aslan & Ulaş Yılmaz | Çağla Çöpürkaya | OK | OK | The view progress in direct proportion to what was analyzed? The links are working correctly? Does the application take place? Are the data transmitted properly? | OK | OK | OK(SUCCESS) | DONE
Feature 16 | Responsive Design | As an user, I want to see all the site in my screen without visual errors. |  |  | Muratcan Tüfekçi & Muhammet Aksoy |  | Çağla Çöpürkaya |  |  | When the scale changes, does the appearance of the project deteriorate? | OK |  | OK(SUCCESS) | DONE
Feature 2
Feature 2
Feature 2
Feature 2
Feature 2
Feature 2
Feature 2
Feature 2
Feature 2
Feature 2
Feature 2
Feature 2
Feature 2
Feature 2
Feature 3
Feature 3
Feature 3
Feature 3
Feature 3
Feature 3
Feature 3
Feature 3
Feature 3
Feature 3
Feature 3
Feature 3
Feature 3
Feature 1-2-3
Feature 4
Feature 4
Feature 4
Feature 4
Feature 4
Feature 4
Feature 4
Feature 4
Feature 5
Feature 5
Feature 5
Feature 5
Feature 5
Feature 5
Feature 5
Feature 5
Feature 5
Feature 6
Feature 6
Feature 6
Feature 6
Feature 6
Feature 6
Feature 7
Feature 7
Feature 7
Feature 7
Feature 7
Feature 7
Feature 7
Feature 7
Feature 7
Feature 8
Feature 8
Feature 8
Feature 8
Feature 8
Feature 8
Feature 8
Feature 8
Feature 8
Feature 8
Feature 8
Feature 8
Feature 8
Feature 9
Feature 9
Feature 9
Feature 10
Feature 10
Feature 10
Feature 10
Feature 10
Feature 10
Feature 10
Feature 11
Feature 11
Feature 11
Feature 11
Feature 11
Feature 11
Feature 11
Feature 11
Feature 11
Feature 11
Feature 11
Feature 11
Feature 11
Feature 11
Feature 11
Feature 12
Feature 12
Feature 12
Feature 12
Feature 13
Feature 13
Feature 13
Feature 13
Feature 13
Feature 14
Feature 14
Feature 14
Feature 14
Feature 14
Feature 14
Feature 14
Feature 14
Feature 14

## SprintPlan
Sprint Number | Start Date | Deadline Date | Deadline Hour | Sprint Goal | Sucess? | Fail Reason
0 | 2021-10-16 | 2012-10-23 | 0:00 | The Distribution of tasks, choose the website design and final decision of functions | OK
1 | 2021-10-24 | 2021-10-31 | 0:00 | Preparing the feasibility report,starting the database | OK
2 | 2021-10-31 | 2021-11-06 | 0:00 | Make database tables,homepage design and analyse. | 80% | Managment problems
3 | 2021-11-06 | 2021-11-13 | 0:00 | Database revision,footer-video-popular products part,analyse and testin environment processes. | OK
4 | 2021-11-13 | 2021-11-20 | 0:00 | Make dynamic database and testing,productbacklog revision on Jira, homepage revision with real data from database,design revision on video part. | OK
5 | 2021-11-20 | 2021-11-27 | 0:00 | Make Products,Processes,Infrastructures pages with API. Solve "Corse error" | 80% | Printsan doesn't send all information
6 | 2021-11-28 | 2021-12-04 | 0:00 | Make Media,Infrustructures(machineparkour),Communication,Carrier pages with API. Testings are keep going. | 80% | Analyst was sick
7 | 2021-12-05 | 2021-12-11 | 0:00 | Make responsive design, media redesign analyz, photograph optimizations, admin paneli, customer meeting | 25% | We could not agree with the company
8 | 2021-12-11 | 2021-12-18 | 0:00 | Make responsive design for Pc Screens,Media tab redesign,admin panel for products and job applys. | 25% | The disruption occurred due to the intensity of the university lectures.
9 | 2021-12-18 | 2021-12-25 | 0:00 | Media tab redesign, admin panel and tests | 80% | Some errors
10 | 2021-11-25 | 2022-01-01 | 0:00 | Recent bug fixes and final tests | 100%

## Meetings
Meeting No | Date | Time | Meeting Name | Member | Role | Attendance
1 | 2021-10-15 | 1:00 | Project Planning | Elif Meriç | Product Owner | joined
1 | 2021-10-15 | 1:00 | Project Planning | Kadir Batuhan Demir | Project Manager | joined
1 | 2021-10-15 | 1:00 | Project Planning | Muratcan Tüfekçi | Front-End Developer | joined
1 | 2021-10-15 | 1:00 | Project Planning | Muhammet Aksoy | Front-End Developer | joined
1 | 2021-10-15 | 1:00 | Project Planning | Çağla Çöpürkaya | Tester | joined
1 | 2021-10-15 | 1:00 | Project Planning | Ulaş Yılmaz | Back-End Developer | joined
1 | 2021-10-15 | 1:00 | Project Planning | Barış Baran Aslan | Database | joined
1 | 2021-10-15 | 1:00 | Project Planning | Abdullah Oranqaı | Analyst | joined
2 | 2021-10-23 | 1:00 | Information Exchange about Product Backlog | Elif Meriç | Product Owner | joined
2 | 2021-10-23 | 1:00 | Information Exchange about Product Backlog | Kadir Batuhan Demir | Project Manager | joined
3 | 2021-10-23 | 2:30 | Project Design and Functional Decision | Elif Meriç | Product Owner | joined
3 | 2021-10-23 | 2:30 | Project Design and Functional Decision | Kadir Batuhan Demir | Project Manager | joined
3 | 2021-10-23 | 2:30 | Project Design and Functional Decision | Muratcan Tüfekçi | Front-End Developer | joined
3 | 2021-10-23 | 2:30 | Project Design and Functional Decision | Muhammet Aksoy | Front-End Developer | joined
3 | 2021-10-23 | 2:30 | Project Design and Functional Decision | Çağla Çöpürkaya | Tester | joined
3 | 2021-10-23 | 2:30 | Project Design and Functional Decision | Ulaş Yılmaz | Back-End Developer | joined
3 | 2021-10-23 | 2:30 | Project Design and Functional Decision | Barış Baran Aslan | Database | joined
3 | 2021-10-23 | 2:30 | Project Design and Functional Decision | Abdullah Oranqaı | Analyst | joined
#N/A
4 | 2021-10-24 | 2:30 | Feasibility Report Preparation | Çağla Çöpürkaya | Tester | joined
4 | 2021-10-24 | 2:30 | Feasibility Report Preparation | Elif Meriç | Product Owner | joined
4 | 2021-10-24 | 2:30 | Feasibility Report Preparation | Abdullah Oranqaı | Analyst | joined
#N/A
5 | 2021-10-26 | 0:15 | Daily Meeting | Elif Meriç | Product Owner | joined
5 | 2021-10-26 | 0:15 | Daily Meeting | Kadir Batuhan Demir | Project Manager | joined
5 | 2021-10-26 | 0:15 | Daily Meeting | Muratcan Tüfekçi | Front-End Developer | joined
5 | 2021-10-26 | 0:15 | Daily Meeting | Muhammet Aksoy | Front-End Developer | joined
5 | 2021-10-26 | 0:15 | Daily Meeting | Çağla Çöpürkaya | Tester | joined
5 | 2021-10-26 | 0:15 | Daily Meeting | Ulaş Yılmaz | Back-End Developer | joined
5 | 2021-10-26 | 0:15 | Daily Meeting | Barış Baran Aslan | Database | joined
5 | 2021-10-26 | 0:15 | Daily Meeting | Abdullah Oranqaı | Analyst | joined
#N/A
6 | 2021-10-27 | 0:30 | Database Design Decision | Elif Meriç | Product Owner | joined
6 | 2021-10-27 | 0:30 | Database Design Decision | Kadir Batuhan Demir | Project Manager | joined
6 | 2021-10-27 | 0:30 | Database Design Decision | Muratcan Tüfekçi | Front-End Developer | joined
6 | 2021-10-27 | 0:30 | Database Design Decision | Muhammet Aksoy | Front-End Developer | joined
6 | 2021-10-27 | 0:30 | Database Design Decision | Çağla Çöpürkaya | Tester | joined
6 | 2021-10-27 | 0:30 | Database Design Decision | Ulaş Yılmaz | Back-End Developer | joined
6 | 2021-10-27 | 0:30 | Database Design Decision | Barış Baran Aslan | Database | joined
6 | 2021-10-27 | 0:30 | Database Design Decision | Abdullah Oranqaı | Analyst | joined
#N/A
7 | 2021-10-30 | 0:20 | Weekly Sprint Meeting | Elif Meriç | Product Owner | joined
7 | 2021-10-30 | 0:20 | Weekly Sprint Meeting | Kadir Batuhan Demir | Project Manager | joined
7 | 2021-10-30 | 0:20 | Weekly Sprint Meeting | Muratcan Tüfekçi | Front-End Developer | joined
7 | 2021-10-30 | 0:20 | Weekly Sprint Meeting | Muhammet Aksoy | Front-End Developer | joined
7 | 2021-10-30 | 0:20 | Weekly Sprint Meeting | Çağla Çöpürkaya | Tester | not joined
7 | 2021-10-30 | 0:20 | Weekly Sprint Meeting | Ulaş Yılmaz | Back-End Developer | joined
7 | 2021-10-30 | 0:20 | Weekly Sprint Meeting | Barış Baran Aslan | Database | joined
7 | 2021-10-30 | 0:20 | Weekly Sprint Meeting | Abdullah Oranqaı | Analyst | not joined
#N/A
8 | 2021-11-02 | 0:30 | Customer Requests Meeting | Elif Meriç | Product Owner | joined
8 | 2021-11-02 | 0:30 | Customer Requests Meeting | Kadir Batuhan Demir | Project Manager | joined
8 | 2021-11-02 | 0:30 | Customer Requests Meeting | Muratcan Tüfekçi | Front-End Developer | joined
8 | 2021-11-02 | 0:30 | Customer Requests Meeting | Muhammet Aksoy | Front-End Developer | joined
8 | 2021-11-02 | 0:30 | Customer Requests Meeting | Çağla Çöpürkaya | Tester | joined
8 | 2021-11-02 | 0:30 | Customer Requests Meeting | Ulaş Yılmaz | Back-End Developer | joined
8 | 2021-11-02 | 0:30 | Customer Requests Meeting | Barış Baran Aslan | Database | joined
8 | 2021-11-02 | 0:30 | Customer Requests Meeting | Abdullah Oranqaı | Analyst | joined
#N/A
9 | 2021-11-06 | 0:30 | Weekly Sprint Meeting-3 | Elif Meriç | Product Owner | joined
9 | 2021-11-06 | 0:30 | Weekly Sprint Meeting-3 | Kadir Batuhan Demir | Project Manager | joined
9 | 2021-11-06 | 0:30 | Weekly Sprint Meeting-3 | Muratcan Tüfekçi | Front-End Developer | joined
9 | 2021-11-06 | 0:30 | Weekly Sprint Meeting-3 | Muhammet Aksoy | Front-End Developer | joined
9 | 2021-11-06 | 0:30 | Weekly Sprint Meeting-3 | Çağla Çöpürkaya | Tester | joined
9 | 2021-11-06 | 0:30 | Weekly Sprint Meeting-3 | Ulaş Yılmaz | Back-End Developer | joined
9 | 2021-11-06 | 0:30 | Weekly Sprint Meeting-3 | Barış Baran Aslan | Database | joined
9 | 2021-11-06 | 0:30 | Weekly Sprint Meeting-3 | Abdullah Oranqaı | Analyst | joined
#N/A
10 | 2021-11-09 | 2:00 | Customer Requests Meeting | Elif Meriç | Product Owner | joined
10 | 2021-11-09 | 2:00 | Customer Requests Meeting | Çağla Çöpürkaya | Tester | joined
#N/A
11 | 2021-11-09 | 0:10 | Showing Design to Customer Meeting | Elif Meriç | Product Owner | joined
11 | 2021-11-09 | 0:10 | Showing Design to Customer Meeting | Kadir Batuhan Demir | Project Manager | joined
11 | 2021-11-09 | 0:10 | Showing Design to Customer Meeting | Muhammet Aksoy | Front-End Developer | joined
11 | 2021-11-09 | 0:10 | Showing Design to Customer Meeting | Abdullah Oranqaı | Analyst | joined
12 | 2021-11-09 | 0:30 | Final Design Meeting | Elif Meriç | Product Owner | joined
12 | 2021-11-09 | 0:30 | Final Design Meeting | Kadir Batuhan Demir | Project Manager | joined
12 | 2021-11-09 | 0:30 | Final Design Meeting | Muratcan Tüfekçi | Front-End Developer | joined
12 | 2021-11-09 | 0:30 | Final Design Meeting | Muhammet Aksoy | Front-End Developer | joined
12 | 2021-11-09 | 0:30 | Final Design Meeting | Çağla Çöpürkaya | Tester | joined
12 | 2021-11-09 | 0:30 | Final Design Meeting | Ulaş Yılmaz | Back-End Developer | joined
12 | 2021-11-09 | 0:30 | Final Design Meeting | Barış Baran Aslan | Database | joined
12 | 2021-11-09 | 0:30 | Final Design Meeting | Abdullah Oranqaı | Analyst | joined
13 | 2021-11-13 | 1:00 | Weekly Sprint Meeting-4 | Elif Meriç | Product Owner | joined
13 | 2021-11-13 | 1:00 | Weekly Sprint Meeting-4 | Kadir Batuhan Demir | Project Manager | joined
13 | 2021-11-13 | 1:00 | Weekly Sprint Meeting-4 | Muratcan Tüfekçi | Front-End Developer | joined
13 | 2021-11-13 | 1:00 | Weekly Sprint Meeting-4 | Muhammet Aksoy | Front-End Developer | joined
13 | 2021-11-13 | 1:00 | Weekly Sprint Meeting-4 | Çağla Çöpürkaya | Tester | joined
13 | 2021-11-13 | 1:00 | Weekly Sprint Meeting-4 | Ulaş Yılmaz | Back-End Developer | not joined
13 | 2021-11-13 | 1:00 | Weekly Sprint Meeting-4 | Barış Baran Aslan | Database | joined
13 | 2021-11-13 | 1:00 | Weekly Sprint Meeting-4 | Abdullah Oranqaı | Analyst | joined
14 | 2021-11-16 | 0:10 | Cors Error Meeting | Muratcan Tüfekçi | Front-End Developer | joined
14 | 2021-11-16 | 0:10 | Cors Error Meeting | Muhammet Aksoy | Front-End Developer | joined
14 | 2021-11-16 | 0:10 | Cors Error Meeting | Ulaş Yılmaz | Back-End Developer | joined
14 | 2021-11-16 | 0:10 | Cors Error Meeting | Barış Baran Aslan | Database | joined
15 | 2021-11-18 | 0:30 | Design Feedback Meeting | Elif Meriç | Product Owner | joined
15 | 2021-11-18 | 0:30 | Design Feedback Meeting | Kadir Batuhan Demir | Project Manager | joined
15 | 2021-11-18 | 0:30 | Design Feedback Meeting | Muratcan Tüfekçi | Front-End Developer | joined
15 | 2021-11-18 | 0:30 | Design Feedback Meeting | Muhammet Aksoy | Front-End Developer | not joined
15 | 2021-11-18 | 0:30 | Design Feedback Meeting | Çağla Çöpürkaya | Tester | joined
15 | 2021-11-18 | 0:30 | Design Feedback Meeting | Ulaş Yılmaz | Back-End Developer | joined
15 | 2021-11-18 | 0:30 | Design Feedback Meeting | Barış Baran Aslan | Database | not joined
15 | 2021-11-18 | 0:30 | Design Feedback Meeting | Abdullah Oranqaı | Analyst | joined
16 | 2021-11-20 | 1:00 | Weekly Sprint Meeting-5 | Elif Meriç | Product Owner | joined
16 | 2021-11-20 | 1:00 | Weekly Sprint Meeting-5 | Kadir Batuhan Demir | Project Manager | joined
16 | 2021-11-20 | 1:00 | Weekly Sprint Meeting-5 | Muratcan Tüfekçi | Front-End Developer | joined
16 | 2021-11-20 | 1:00 | Weekly Sprint Meeting-5 | Muhammet Aksoy | Front-End Developer | joined
16 | 2021-11-20 | 1:00 | Weekly Sprint Meeting-5 | Çağla Çöpürkaya | Tester | joined
16 | 2021-11-20 | 1:00 | Weekly Sprint Meeting-5 | Ulaş Yılmaz | Back-End Developer | joined
16 | 2021-11-20 | 1:00 | Weekly Sprint Meeting-5 | Barış Baran Aslan | Database | joined
16 | 2021-11-20 | 1:00 | Weekly Sprint Meeting-5 | Abdullah Oranqaı | Analyst | joined
17 | 2021-11-25 | 0:30 | Daily Feedback Meeting | Elif Meriç | Product Owner | joined
17 | 2021-11-25 | 0:30 | Daily Feedback Meeting | Kadir Batuhan Demir | Project Manager | joined
17 | 2021-11-25 | 0:30 | Daily Feedback Meeting | Muratcan Tüfekçi | Front-End Developer | joined
17 | 2021-11-25 | 0:30 | Daily Feedback Meeting | Muhammet Aksoy | Front-End Developer | joined
17 | 2021-11-25 | 0:30 | Daily Feedback Meeting | Çağla Çöpürkaya | Tester | joined
17 | 2021-11-25 | 0:30 | Daily Feedback Meeting | Ulaş Yılmaz | Back-End Developer | not joined
17 | 2021-11-25 | 0:30 | Daily Feedback Meeting | Barış Baran Aslan | Database | not joined
17 | 2021-11-25 | 0:30 | Daily Feedback Meeting | Abdullah Oranqaı | Analyst | joined
18 | 2021-11-26 | 2:00 | Customer Meeting with Printsan | Elif Meriç | Product Owner | joined
18 | 2021-11-27 | 1:00 | Weekly Sprint Meeting-6 | Elif Meriç | Product Owner | joined
18 | 2021-11-27 | 1:00 | Weekly Sprint Meeting-6 | Kadir Batuhan Demir | Project Manager | joined
18 | 2021-11-27 | 1:00 | Weekly Sprint Meeting-6 | Muratcan Tüfekçi | Front-End Developer | joined
18 | 2021-11-27 | 1:00 | Weekly Sprint Meeting-6 | Muhammet Aksoy | Front-End Developer | joined
18 | 2021-11-27 | 1:00 | Weekly Sprint Meeting-6 | Çağla Çöpürkaya | Tester | joined
18 | 2021-11-27 | 1:00 | Weekly Sprint Meeting-6 | Ulaş Yılmaz | Back-End Developer | joined
18 | 2021-11-27 | 1:00 | Weekly Sprint Meeting-6 | Barış Baran Aslan | Database | joined
18 | 2021-11-27 | 1:00 | Weekly Sprint Meeting-6 | Abdullah Oranqaı | Analyst | joined
19 | 2021-11-30 | 0:30 | Daily Feedback Meeting | Elif Meriç | Product Owner | joined
19 | 2021-11-30 | 0:30 | Daily Feedback Meeting | Kadir Batuhan Demir | Project Manager | joined
19 | 2021-11-30 | 0:30 | Daily Feedback Meeting | Muratcan Tüfekçi | Front-End Developer | joined
19 | 2021-11-30 | 0:30 | Daily Feedback Meeting | Muhammet Aksoy | Front-End Developer | joined
19 | 2021-11-30 | 0:30 | Daily Feedback Meeting | Çağla Çöpürkaya | Tester | joined
19 | 2021-11-30 | 0:30 | Daily Feedback Meeting | Ulaş Yılmaz | Back-End Developer | not joined
19 | 2021-11-30 | 0:30 | Daily Feedback Meeting | Barış Baran Aslan | Database | joined
19 | 2021-11-30 | 0:30 | Daily Feedback Meeting | Abdullah Oranqaı | Analyst | joined
20 | 2021-12-02 | 0:30 | Design Feedback Meeting | Elif Meriç | Product Owner | joined
20 | 2021-12-02 | 0:30 | Design Feedback Meeting | Kadir Batuhan Demir | Project Manager | joined
20 | 2021-12-02 | 0:30 | Design Feedback Meeting | Muratcan Tüfekçi | Front-End Developer | joined
20 | 2021-12-02 | 0:30 | Design Feedback Meeting | Muhammet Aksoy | Front-End Developer | joined
20 | 2021-12-02 | 0:30 | Design Feedback Meeting | Çağla Çöpürkaya | Tester | joined
20 | 2021-12-02 | 0:30 | Design Feedback Meeting | Ulaş Yılmaz | Back-End Developer | joined
20 | 2021-12-02 | 0:30 | Design Feedback Meeting | Barış Baran Aslan | Database | not joined
20 | 2021-12-02 | 0:30 | Design Feedback Meeting | Abdullah Oranqaı | Analyst | not joined
21 | 2021-12-04 | 1:00 | Weekly Sprint Meeting-7 | Elif Meriç | Product Owner | joined
21 | 2021-12-04 | 1:00 | Weekly Sprint Meeting-7 | Kadir Batuhan Demir | Project Manager | joined
21 | 2021-12-04 | 1:00 | Weekly Sprint Meeting-7 | Muratcan Tüfekçi | Front-End Developer | joined
21 | 2021-12-04 | 1:00 | Weekly Sprint Meeting-7 | Muhammet Aksoy | Front-End Developer | joined
21 | 2021-12-04 | 1:00 | Weekly Sprint Meeting-7 | Çağla Çöpürkaya | Tester | joined
21 | 2021-12-04 | 1:00 | Weekly Sprint Meeting-7 | Ulaş Yılmaz | Back-End Developer | joined
21 | 2021-12-04 | 1:00 | Weekly Sprint Meeting-7 | Barış Baran Aslan | Database | joined
21 | 2021-12-04 | 1:00 | Weekly Sprint Meeting-7 | Abdullah Oranqaı | Analyst | joined
22 | 2021-12-09 | 1:00 | Customer Meeting with Printsan | Elif Meriç | Product Owner | joined
22 | 2021-12-09 | 1:00 | Customer Meeting with Printsan | Kadir Batuhan Demir | Project Manager | joined
23 | 2021-12-11 | 1:00 | Weekly Sprint Meeting-8 | Elif Meriç | Product Owner | joined
23 | 2021-12-11 | 1:00 | Weekly Sprint Meeting-8 | Kadir Batuhan Demir | Project Manager | joined
23 | 2021-12-11 | 1:00 | Weekly Sprint Meeting-8 | Muratcan Tüfekçi | Front-End Developer | joined
23 | 2021-12-11 | 1:00 | Weekly Sprint Meeting-8 | Muhammet Aksoy | Front-End Developer | joined
23 | 2021-12-11 | 1:00 | Weekly Sprint Meeting-8 | Çağla Çöpürkaya | Tester | joined
23 | 2021-12-11 | 1:00 | Weekly Sprint Meeting-8 | Ulaş Yılmaz | Back-End Developer | joined
23 | 2021-12-11 | 1:00 | Weekly Sprint Meeting-8 | Barış Baran Aslan | Database | joined
23 | 2021-12-11 | 1:00 | Weekly Sprint Meeting-8 | Abdullah Oranqaı | Analyst | joined
24 | 2021-12-15 | 1:00 | Admin Panel Meeting | Muratcan Tüfekçi | Front-End Developer | joined
24 | 2021-12-15 | 1:00 | Admin Panel Meeting | Muhammet Aksoy | Front-End Developer | joined
25 | 2021-12-16 | 0:30 | Daily Meeting | Elif Meriç | Product Owner | joined
25 | 2021-12-16 | 0:30 | Daily Meeting | Kadir Batuhan Demir | Project Manager | joined
25 | 2021-12-16 | 0:30 | Daily Meeting | Muratcan Tüfekçi | Front-End Developer | joined
25 | 2021-12-16 | 0:30 | Daily Meeting | Muhammet Aksoy | Front-End Developer | joined
25 | 2021-12-16 | 0:30 | Daily Meeting | Çağla Çöpürkaya | Tester | joined
25 | 2021-12-16 | 0:30 | Daily Meeting | Ulaş Yılmaz | Back-End Developer | not joined
25 | 2021-12-16 | 0:30 | Daily Meeting | Barış Baran Aslan | Database | joined
25 | 2021-12-16 | 0:30 | Daily Meeting | Abdullah Oranqaı | Analyst | joined
26 | 2021-12-18 | 0:45 | Weekly Sprint Meeting-9 | Elif Meriç | Product Owner | joined
26 | 2021-12-18 | 0:45 | Weekly Sprint Meeting-9 | Kadir Batuhan Demir | Project Manager | joined
26 | 2021-12-18 | 0:45 | Weekly Sprint Meeting-9 | Muratcan Tüfekçi | Front-End Developer | joined
26 | 2021-12-18 | 0:45 | Weekly Sprint Meeting-9 | Muhammet Aksoy | Front-End Developer | joined
26 | 2021-12-18 | 0:45 | Weekly Sprint Meeting-9 | Çağla Çöpürkaya | Tester | joined
26 | 2021-12-18 | 0:45 | Weekly Sprint Meeting-9 | Ulaş Yılmaz | Back-End Developer | joined
26 | 2021-12-18 | 0:45 | Weekly Sprint Meeting-9 | Barış Baran Aslan | Database | joined
26 | 2021-12-18 | 0:45 | Weekly Sprint Meeting-9 | Abdullah Oranqaı | Analyst | joined
27 | 2021-12-23 | 0:45 | Final Meeting | Elif Meriç | Product Owner | joined
27 | 2021-12-23 | 0:45 | Final Meeting | Kadir Batuhan Demir | Project Manager | joined
27 | 2021-12-23 | 0:45 | Final Meeting | Muratcan Tüfekçi | Front-End Developer | joined
27 | 2021-12-23 | 0:45 | Final Meeting | Muhammet Aksoy | Front-End Developer | joined
27 | 2021-12-23 | 0:45 | Final Meeting | Çağla Çöpürkaya | Tester | joined
27 | 2021-12-23 | 0:45 | Final Meeting | Ulaş Yılmaz | Back-End Developer | joined
27 | 2021-12-23 | 0:45 | Final Meeting | Barış Baran Aslan | Database | joined
27 | 2021-12-23 | 0:45 | Final Meeting | Abdullah Oranqaı | Analyst | joined
28 | 2021-12-23 | 1:00 | Test and Presentation Meeting | Elif Meriç | Product Owner | joined
28 | 2021-12-23 | 1:00 | Test and Presentation Meeting | Kadir Batuhan Demir | Project Manager | joined
28 | 2021-12-23 | 1:00 | Test and Presentation Meeting | Muratcan Tüfekçi | Front-End Developer | joined
28 | 2021-12-23 | 1:00 | Test and Presentation Meeting | Muhammet Aksoy | Front-End Developer | joined
28 | 2021-12-23 | 1:00 | Test and Presentation Meeting | Çağla Çöpürkaya | Tester | joined
28 | 2021-12-23 | 1:00 | Test and Presentation Meeting | Ulaş Yılmaz | Back-End Developer | joined
28 | 2021-12-23 | 1:00 | Test and Presentation Meeting | Barış Baran Aslan | Database | joined
28 | 2021-12-23 | 1:00 | Test and Presentation Meeting | Abdullah Oranqaı | Analyst | joined
#N/A
#N/A
#N/A
29 | 2021-12-28 | 1:00 | Test and Presentation Meeting-2 | Elif Meriç | Product Owner | joined
29 | 2021-12-28 | 1:00 | Test and Presentation Meeting-2 | Kadir Batuhan Demir | Project Manager | joined
29 | 2021-12-28 | 1:00 | Test and Presentation Meeting-2 | Muratcan Tüfekçi | Front-End Developer | joined
29 | 2021-12-28 | 1:00 | Test and Presentation Meeting-2 | Muhammet Aksoy | Front-End Developer | joined
29 | 2021-12-28 | 1:00 | Test and Presentation Meeting-2 | Çağla Çöpürkaya | Tester | joined
29 | 2021-12-28 | 1:00 | Test and Presentation Meeting-2 | Ulaş Yılmaz | Back-End Developer | joined
29 | 2021-12-28 | 1:00 | Test and Presentation Meeting-2 | Barış Baran Aslan | Database | joined
29 | 2021-12-28 | 1:00 | Test and Presentation Meeting-2 | Abdullah Oranqaı | Analyst | joined
#N/A
#N/A
#N/A
30 | 2021-12-31 | 1:00 | Test and Presentation Meeting-3 | Elif Meriç | Product Owner | joined
30 | 2021-12-31 | 1:00 | Test and Presentation Meeting-3 | Kadir Batuhan Demir | Project Manager | joined
30 | 2021-12-31 | 1:00 | Test and Presentation Meeting-3 | Muratcan Tüfekçi | Front-End Developer | joined
30 | 2021-12-31 | 1:00 | Test and Presentation Meeting-3 | Muhammet Aksoy | Front-End Developer | joined
30 | 2021-12-31 | 1:00 | Test and Presentation Meeting-3 | Çağla Çöpürkaya | Tester | joined
30 | 2021-12-31 | 1:00 | Test and Presentation Meeting-3 | Ulaş Yılmaz | Back-End Developer | joined
30 | 2021-12-31 | 1:00 | Test and Presentation Meeting-3 | Barış Baran Aslan | Database | joined
30 | 2021-12-31 | 1:00 | Test and Presentation Meeting-3 | Abdullah Oranqaı | Analyst | joined
16 |  |  |  |  | #N/A
16 |  |  |  |  | #N/A
16 |  |  |  |  | #N/A
16 |  |  |  |  | #N/A
16 |  |  |  |  | #N/A
16 |  |  |  |  | #N/A
16 |  |  |  |  | #N/A
16 |  |  |  |  | #N/A
16 |  |  |  |  | #N/A
16 |  |  |  |  | #N/A
16 |  |  |  |  | #N/A
16 |  |  |  |  | #N/A
#N/A
17 |  |  |  |  | #N/A
17 |  |  |  |  | #N/A
17 |  |  |  |  | #N/A
17 |  |  |  |  | #N/A
17 |  |  |  |  | #N/A
17 |  |  |  |  | #N/A
17 |  |  |  |  | #N/A
17 |  |  |  |  | #N/A
17 |  |  |  |  | #N/A
17 |  |  |  |  | #N/A
17 |  |  |  |  | #N/A
17 |  |  |  |  | #N/A
17 |  |  |  |  | #N/A
17 |  |  |  |  | #N/A
17 |  |  |  |  | #N/A
17 |  |  |  |  | #N/A
17 |  |  |  |  | #N/A
17 |  |  |  |  | #N/A
17 |  |  |  |  | #N/A
17 |  |  |  |  | #N/A
17 |  |  |  |  | #N/A
17 |  |  |  |  | #N/A
17 |  |  |  |  | #N/A
17 |  |  |  |  | #N/A
#N/A
18 |  |  |  |  | #N/A
18 |  |  |  |  | #N/A
18 |  |  |  |  | #N/A
18 |  |  |  |  | #N/A
18 |  |  |  |  | #N/A
18 |  |  |  |  | #N/A
18 |  |  |  |  | #N/A
18 |  |  |  |  | #N/A
18 |  |  |  |  | #N/A
18 |  |  |  |  | #N/A
18 |  |  |  |  | #N/A
18 |  |  |  |  | #N/A
18 |  |  |  |  | #N/A
18 |  |  |  |  | #N/A
18 |  |  |  |  | #N/A
18 |  |  |  |  | #N/A
18 |  |  |  |  | #N/A
18 |  |  |  |  | #N/A
18 |  |  |  |  | #N/A
18 |  |  |  |  | #N/A
18 |  |  |  |  | #N/A
18 |  |  |  |  | #N/A
18 |  |  |  |  | #N/A
18 |  |  |  |  | #N/A
#N/A
19 |  |  |  |  | #N/A
19 |  |  |  |  | #N/A
19 |  |  |  |  | #N/A
19 |  |  |  |  | #N/A
19 |  |  |  |  | #N/A
19 |  |  |  |  | #N/A
19 |  |  |  |  | #N/A
19 |  |  |  |  | #N/A
19 |  |  |  |  | #N/A
19 |  |  |  |  | #N/A
19 |  |  |  |  | #N/A
19 |  |  |  |  | #N/A
19 |  |  |  |  | #N/A
19 |  |  |  |  | #N/A
19 |  |  |  |  | #N/A
19 |  |  |  |  | #N/A
19 |  |  |  |  | #N/A
19 |  |  |  |  | #N/A
19 |  |  |  |  | #N/A
19 |  |  |  |  | #N/A
19 |  |  |  |  | #N/A
19 |  |  |  |  | #N/A
19 |  |  |  |  | #N/A
19 |  |  |  |  | #N/A
#N/A
20 |  |  |  |  | #N/A
20 |  |  |  |  | #N/A
20 |  |  |  |  | #N/A
20 |  |  |  |  | #N/A
20 |  |  |  |  | #N/A
20 |  |  |  |  | #N/A
20 |  |  |  |  | #N/A
20 |  |  |  |  | #N/A
20 |  |  |  |  | #N/A
20 |  |  |  |  | #N/A
20 |  |  |  |  | #N/A
20 |  |  |  |  | #N/A
20 |  |  |  |  | #N/A
20 |  |  |  |  | #N/A
20 |  |  |  |  | #N/A
20 |  |  |  |  | #N/A
20 |  |  |  |  | #N/A
20 |  |  |  |  | #N/A
20 |  |  |  |  | #N/A
20 |  |  |  |  | #N/A
20 |  |  |  |  | #N/A
20 |  |  |  |  | #N/A
20 |  |  |  |  | #N/A
20 |  |  |  |  | #N/A
#N/A
21 |  |  |  |  | #N/A
21 |  |  |  |  | #N/A
21 |  |  |  |  | #N/A
21 |  |  |  |  | #N/A
21 |  |  |  |  | #N/A
21 |  |  |  |  | #N/A
21 |  |  |  |  | #N/A
21 |  |  |  |  | #N/A
21 |  |  |  |  | #N/A
21 |  |  |  |  | #N/A
21 |  |  |  |  | #N/A
21 |  |  |  |  | #N/A
21 |  |  |  |  | #N/A
21 |  |  |  |  | #N/A
21 |  |  |  |  | #N/A
21 |  |  |  |  | #N/A
21 |  |  |  |  | #N/A
21 |  |  |  |  | #N/A
21 |  |  |  |  | #N/A
21 |  |  |  |  | #N/A
21 |  |  |  |  | #N/A
21 |  |  |  |  | #N/A
21 |  |  |  |  | #N/A
21 |  |  |  |  | #N/A
#N/A
22 |  |  |  |  | #N/A
22 |  |  |  |  | #N/A
22 |  |  |  |  | #N/A
22 |  |  |  |  | #N/A
22 |  |  |  |  | #N/A
22 |  |  |  |  | #N/A
22 |  |  |  |  | #N/A
22 |  |  |  |  | #N/A
22 |  |  |  |  | #N/A
22 |  |  |  |  | #N/A
22 |  |  |  |  | #N/A
22 |  |  |  |  | #N/A
22 |  |  |  |  | #N/A
22 |  |  |  |  | #N/A
22 |  |  |  |  | #N/A
22 |  |  |  |  | #N/A
22 |  |  |  |  | #N/A
22 |  |  |  |  | #N/A
22 |  |  |  |  | #N/A
22 |  |  |  |  | #N/A
22 |  |  |  |  | #N/A
22 |  |  |  |  | #N/A
22 |  |  |  |  | #N/A
22 |  |  |  |  | #N/A
#N/A
23 |  |  |  |  | #N/A
23 |  |  |  |  | #N/A
23 |  |  |  |  | #N/A
23 |  |  |  |  | #N/A
23 |  |  |  |  | #N/A
23 |  |  |  |  | #N/A
23 |  |  |  |  | #N/A
23 |  |  |  |  | #N/A
23 |  |  |  |  | #N/A
23 |  |  |  |  | #N/A
23 |  |  |  |  | #N/A
23 |  |  |  |  | #N/A
23 |  |  |  |  | #N/A
23 |  |  |  |  | #N/A
23 |  |  |  |  | #N/A
23 |  |  |  |  | #N/A
23 |  |  |  |  | #N/A
23 |  |  |  |  | #N/A
23 |  |  |  |  | #N/A
23 |  |  |  |  | #N/A
23 |  |  |  |  | #N/A
23 |  |  |  |  | #N/A
23 |  |  |  |  | #N/A
23 |  |  |  |  | #N/A
#N/A
24 |  |  |  |  | #N/A
24 |  |  |  |  | #N/A
24 |  |  |  |  | #N/A
24 |  |  |  |  | #N/A
24 |  |  |  |  | #N/A
24 |  |  |  |  | #N/A
24 |  |  |  |  | #N/A
24 |  |  |  |  | #N/A
24 |  |  |  |  | #N/A
24 |  |  |  |  | #N/A
24 |  |  |  |  | #N/A
24 |  |  |  |  | #N/A
24 |  |  |  |  | #N/A
24 |  |  |  |  | #N/A
24 |  |  |  |  | #N/A
24 |  |  |  |  | #N/A
24 |  |  |  |  | #N/A
24 |  |  |  |  | #N/A
24 |  |  |  |  | #N/A
24 |  |  |  |  | #N/A
24 |  |  |  |  | #N/A
24 |  |  |  |  | #N/A
24 |  |  |  |  | #N/A
24 |  |  |  |  | #N/A
#N/A
25 |  |  |  |  | #N/A
25 |  |  |  |  | #N/A
25 |  |  |  |  | #N/A
25 |  |  |  |  | #N/A
25 |  |  |  |  | #N/A
25 |  |  |  |  | #N/A
25 |  |  |  |  | #N/A
25 |  |  |  |  | #N/A
25 |  |  |  |  | #N/A
25 |  |  |  |  | #N/A
25 |  |  |  |  | #N/A
25 |  |  |  |  | #N/A
25 |  |  |  |  | #N/A
25 |  |  |  |  | #N/A
25 |  |  |  |  | #N/A
25 |  |  |  |  | #N/A
25 |  |  |  |  | #N/A
25 |  |  |  |  | #N/A
25 |  |  |  |  | #N/A
25 |  |  |  |  | #N/A
25 |  |  |  |  | #N/A
25 |  |  |  |  | #N/A
25 |  |  |  |  | #N/A
25 |  |  |  |  | #N/A
#N/A
26 |  |  |  |  | #N/A
26 |  |  |  |  | #N/A
26 |  |  |  |  | #N/A
26 |  |  |  |  | #N/A
26 |  |  |  |  | #N/A
26 |  |  |  |  | #N/A
26 |  |  |  |  | #N/A
26 |  |  |  |  | #N/A
26 |  |  |  |  | #N/A
26 |  |  |  |  | #N/A
26 |  |  |  |  | #N/A
26 |  |  |  |  | #N/A
26 |  |  |  |  | #N/A
26 |  |  |  |  | #N/A
26 |  |  |  |  | #N/A
26 |  |  |  |  | #N/A
26 |  |  |  |  | #N/A
26 |  |  |  |  | #N/A
26 |  |  |  |  | #N/A
26 |  |  |  |  | #N/A
26 |  |  |  |  | #N/A
26 |  |  |  |  | #N/A
26 |  |  |  |  | #N/A
26 |  |  |  |  | #N/A
#N/A
27 |  |  |  |  | #N/A
27 |  |  |  |  | #N/A
27 |  |  |  |  | #N/A
27 |  |  |  |  | #N/A
27 |  |  |  |  | #N/A
27 |  |  |  |  | #N/A
27 |  |  |  |  | #N/A
27 |  |  |  |  | #N/A
27 |  |  |  |  | #N/A
27 |  |  |  |  | #N/A
27 |  |  |  |  | #N/A
27 |  |  |  |  | #N/A
27 |  |  |  |  | #N/A
27 |  |  |  |  | #N/A
27 |  |  |  |  | #N/A
27 |  |  |  |  | #N/A
27 |  |  |  |  | #N/A
27 |  |  |  |  | #N/A
27 |  |  |  |  | #N/A
27 |  |  |  |  | #N/A
27 |  |  |  |  | #N/A
27 |  |  |  |  | #N/A
27 |  |  |  |  | #N/A
27 |  |  |  |  | #N/A
#N/A
28 |  |  |  |  | #N/A
28 |  |  |  |  | #N/A
28 |  |  |  |  | #N/A
28 |  |  |  |  | #N/A
28 |  |  |  |  | #N/A
28 |  |  |  |  | #N/A
28 |  |  |  |  | #N/A
28 |  |  |  |  | #N/A
28 |  |  |  |  | #N/A
28 |  |  |  |  | #N/A
28 |  |  |  |  | #N/A
28 |  |  |  |  | #N/A
28 |  |  |  |  | #N/A
28 |  |  |  |  | #N/A
28 |  |  |  |  | #N/A
28 |  |  |  |  | #N/A
28 |  |  |  |  | #N/A
28 |  |  |  |  | #N/A
28 |  |  |  |  | #N/A
28 |  |  |  |  | #N/A
28 |  |  |  |  | #N/A
28 |  |  |  |  | #N/A
28 |  |  |  |  | #N/A
28 |  |  |  |  | #N/A
#N/A
29 |  |  |  |  | #N/A
29 |  |  |  |  | #N/A
29 |  |  |  |  | #N/A
29 |  |  |  |  | #N/A
29 |  |  |  |  | #N/A
29 |  |  |  |  | #N/A
29 |  |  |  |  | #N/A
29 |  |  |  |  | #N/A
29 |  |  |  |  | #N/A
29 |  |  |  |  | #N/A
29 |  |  |  |  | #N/A
29 |  |  |  |  | #N/A
29 |  |  |  |  | #N/A
29 |  |  |  |  | #N/A
29 |  |  |  |  | #N/A
29 |  |  |  |  | #N/A
29 |  |  |  |  | #N/A
29 |  |  |  |  | #N/A
29 |  |  |  |  | #N/A
29 |  |  |  |  | #N/A
29 |  |  |  |  | #N/A
29 |  |  |  |  | #N/A
29 |  |  |  |  | #N/A
29 |  |  |  |  | #N/A
#N/A
30 |  |  |  |  | #N/A
30 |  |  |  |  | #N/A
30 |  |  |  |  | #N/A
30 |  |  |  |  | #N/A
30 |  |  |  |  | #N/A
30 |  |  |  |  | #N/A
30 |  |  |  |  | #N/A
30 |  |  |  |  | #N/A
30 |  |  |  |  | #N/A
30 |  |  |  |  | #N/A
30 |  |  |  |  | #N/A
30 |  |  |  |  | #N/A
30 |  |  |  |  | #N/A
30 |  |  |  |  | #N/A
30 |  |  |  |  | #N/A
30 |  |  |  |  | #N/A
30 |  |  |  |  | #N/A
30 |  |  |  |  | #N/A
30 |  |  |  |  | #N/A
30 |  |  |  |  | #N/A
30 |  |  |  |  | #N/A
30 |  |  |  |  | #N/A
30 |  |  |  |  | #N/A
30 |  |  |  |  | #N/A
#N/A
31 |  |  |  |  | #N/A
31 |  |  |  |  | #N/A
31 |  |  |  |  | #N/A
31 |  |  |  |  | #N/A
31 |  |  |  |  | #N/A
31 |  |  |  |  | #N/A
31 |  |  |  |  | #N/A
31 |  |  |  |  | #N/A
31 |  |  |  |  | #N/A
31 |  |  |  |  | #N/A
31 |  |  |  |  | #N/A
31 |  |  |  |  | #N/A
31 |  |  |  |  | #N/A
31 |  |  |  |  | #N/A
31 |  |  |  |  | #N/A
31 |  |  |  |  | #N/A
#N/A
32 |  |  |  |  | #N/A
32 |  |  |  |  | #N/A
32 |  |  |  |  | #N/A
32 |  |  |  |  | #N/A
32 |  |  |  |  | #N/A
32 |  |  |  |  | #N/A
#N/A
33 |  |  |  |  | #N/A
33 |  |  |  |  | #N/A
33 |  |  |  |  | #N/A
33 |  |  |  |  | #N/A
33 |  |  |  |  | #N/A
33 |  |  |  |  | #N/A
33 |  |  |  |  | #N/A
33 |  |  |  |  | #N/A
33 |  |  |  |  | #N/A
33 |  |  |  |  | #N/A
33 |  |  |  |  | #N/A
33 |  |  |  |  | #N/A
33 |  |  |  |  | #N/A
33 |  |  |  |  | #N/A
33 |  |  |  |  | #N/A
33 |  |  |  |  | #N/A
33 |  |  |  |  | #N/A
33 |  |  |  |  | #N/A
33 |  |  |  |  | #N/A
33 |  |  |  |  | #N/A
33 |  |  |  |  | #N/A
33 |  |  |  |  | #N/A
33 |  |  |  |  | #N/A
33 |  |  |  |  | #N/A
#N/A
34 |  |  |  |  | #N/A
34 |  |  |  |  | #N/A
34 |  |  |  |  | #N/A
34 |  |  |  |  | #N/A
34 |  |  |  |  | #N/A
34 |  |  |  |  | #N/A
34 |  |  |  |  | #N/A
34 |  |  |  |  | #N/A
#N/A
35 |  |  |  |  | #N/A
35 |  |  |  |  | #N/A
35 |  |  |  |  | #N/A
35 |  |  |  |  | #N/A
35 |  |  |  |  | #N/A
35 |  |  |  |  | #N/A
35 |  |  |  |  | #N/A
35 |  |  |  |  | #N/A
35 |  |  |  |  | #N/A
35 |  |  |  |  | #N/A
35 |  |  |  |  | #N/A
35 |  |  |  |  | #N/A
35 |  |  |  |  | #N/A
35 |  |  |  |  | #N/A
35 |  |  |  |  | #N/A
35 |  |  |  |  | #N/A
35 |  |  |  |  | #N/A
35 |  |  |  |  | #N/A
35 |  |  |  |  | #N/A
35 |  |  |  |  | #N/A
35 |  |  |  |  | #N/A
35 |  |  |  |  | #N/A
35 |  |  |  |  | #N/A
35 |  |  |  |  | #N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A

## MeetingReport
Team Member | Planned # of Meetings | Actual # of Meetings | Missing Meetings | Ratio for Planned vs Actual Meetings
Elif Meriç | 30 | 28 | 2 | 93.33%
Kadir Batuhan Demir | 30 | 25 | 5 | 83.33%
Muratcan Tüfekçi | 30 | 26 | 4 | 86.67%
Muhammet Aksoy | 30 | 25 | 5 | 83.33%
Çağla Çöpürkaya | 30 | 24 | 6 | 80%
Ulaş Yılmaz | 30 | 20 | 10 | 66.67%
Barış Baran Aslan | 30 | 21 | 9 | 70%
Abdullah Oranqaı | 30 | 23 | 7 | 76.67%